## Slide 1: AN OVERVIEW of PROJECT PLANNING

## Slide 2: Contents
Introduction to step wise project planning
Ten steps of a project plan

## Slide 3: Introduction to Step Wise project Planning
This section describes a framework of basic steps in project planning on which the following course contents are build.
The described framework is called the Step Wise Method.

## Slide 4: An Overview of Step Wise Planning

## Slide 5: Case Study
Brigette has been working for the management services department of a local authority when she sees an advertisement for the position of information systems development officer at brightmouth college. She is attracted to the idea of being her own boss, working in a relatively small organization and helping them to setup appropriate information systems from scratch. She applies for the job and get it. One of the first tasks that confronts her is the implementation of independent payroll processing.

## Slide 6: Step 0: Select Project
Called Step 0 because it is actually outside the main project planning steps.
While feasibility study suggests that there is a business case for the project, it would still need to be established that it should have priority over other projects.
This evaluation can be part of project portfolio management.

## Slide 7: Step 1: Identify Project Scope and Objectives
Identify objectives and practical measures of the effectiveness in meeting those objectives
Establish a project authority
Stakeholder analysis – identify all stakeholders in the project and their interests
Modify objectives in the light of stakeholder analysis
Establish methods of communication with all parties

## Slide 8: Step 1: Identify Project Scope and Objectives
Activity 1: List objectives and Identify the main stakeholders and project authority in the provided scenario.

## Slide 9: Step 2: Identify Project Infrastructure
Identify relationship between the project and strategic planning
Identify installation standards and procedures
Identify project team organization
Activity 2: List some standards that brigette should identify and set before moving on further.

## Slide 10: Step 3: Analyze Project Characteristics
Distinguish the project as either objective- or product-driven
Analyze other project characteristics
Identify high-level project risks
Take into account user requirements concerning implementation
Select development methodology and life- cycle approach
Review overall resource estimates

## Slide 11: Step 3: Analyze Project Characteristics
Activity 3: Prepare a list of risks, that you think brigette will identify in this step.

## Slide 12: Step 4: Identify Project Products & Activities
Identify and describe project products
Document generic product flows
Recognize product instances
Produce ideal activity network
Modify the ideal to take into account need for stages and checkpoints

## Slide 13: Step 4: Identify Project Products & Activities
Activity 4: At brightmouth college, Brigette has decided that the finance department at the college should carry out acceptance testing of the new payroll system. The staff are not sure what test documents should look like, Brigette draws up a product description of a test case. Write the content for this product description.

## Slide 14: Step 5: Estimate Effort for Each Activity
Carry out bottom-up estimates
Revise plan to create controllable activities

## Slide 15: Step 6: Identify Activity Risks
Identify and quantify activity-based risks
Plan risk reduction and contingency measures where appropriate
Adjust overall plans and estimates to take account of risks
Activity 5: Brigette identifies as a risk the possible absence of key staff when investigating the user requirements, as this activity will take place over the holiday period. How can she reduce this risk?

## Slide 16: Step 7: Allocate Resources
Identify and allocate resources
Revise plans and estimates to take into account resource constraints

## Slide 17: Step 8: Review/Publicize Plan
Review quality aspects of the project plan
Document plans and obtain agreement

## Slide 18: Steps 9/10: Execute Plan/ Lower Levels of Planning
Once the project is under way, plans will need to be drawn up in greater detail for each activity as it becomes due.
Detailed planning of the later stages will need to be delayed because more information will be available nearer the start of the stage.
It is necessary to make provisional plans for the more distant tasks.

## Slide 19: Activity 6
List the products created by the step wise planning process.

## Slide 20: Summary
Any planning approach should have the following elements:
  the establishment of project objectives
  the analysis of the characteristics of the project
  the establishment of an infrastructure consisting of an appropriate organization and set of standards, methods and tools
  the identification of the products of the project and the activities needed to generate those products
  the allocation of resources to activities
  the establishment of quality controls
  Project planning is an iterative process
  As the time approaches for particular activities to be carried out they should be re-planned in more detail.

## Slide 21: Reading
[Chapter 3] “Software Project Management by Bob Hughes and Mike Cotterell, McGraw-Hill Education; 6th Edition (2009). ISBN-10: 0077122798”