## Slide 1: SOFTWARE EFFORT ESTIMATION

## Slide 2: Contents
Introduction
Difficulties in Estimation
Where are the estimates done?
Problems with over and under estimates
Basis for software estimation
Software effort estimation techniques
Function Points Mark II
COCOMO II: A parametric productivity model
Cost Estimation

## Slide 3: Introduction
A successful project is one that is delivered
  On time
  Within budget
  With the required functionality
It means that targets are estimated and set for all these aspects, and project manager then tries to meet those targets.
Real estimates are crucial, because of incorrect estimates, a project cannot meet its deadline.

## Slide 4: Difficulties in Estimation
Nature of software .
  Complexity and invisibility of software .
Subjective nature of estimating
  Under-estimating small tasks
  Over-estimating large ones .
Political pressures
  Different objectives of people in an organization
  Managers may wish to reduce estimated costs in order to win support for acceptance of a project proposal
Notes: Specialized estimating group

## Slide 5: Difficulties in Estimation
Changing technologies
  Technology is rapidly changing , making the experience of previous project estimates difficult to use in new ones .
Lack of homogeneity of project experience
  Experience on one project may not be applicable to another.

## Slide 6: Where are the Estimates done?
Estimates are carried out at different stages of a software project for a variety of reasons .
Feasibility study
  Estimates here conforms that the benefits of the potential system will justify the costs
Strategic planning
  Project portfolio management is involved here. Benefits and costs of new projects are estimated to allocate priorities .

## Slide 7: Where are the Estimates done?
System specification
  Design of a system shows that how user requirements will be fulfilled .
  Different design approaches can be considered for a single requirement specification.
  The effort needed to implement different design proposals is estimated here.
  Estimates at the design stage will also confirm that the feasibility study is still valid.

## Slide 8: Where are the Estimates done?
Evaluation of suppliers proposals
  A manager could consider putting development out to tender.
  Potential contractors would examine the system specifications and produce estimates ( their bid ).
  The manager can still produce his own estimates why ?
    To question a bid that seems too low which could be an indication of a bad understanding of the system specifications .
    Or to compare the bids to in-house development

## Slide 9: Where are the Estimates done?
Project planning
  As the planning and implementation of the project becomes more detailed, more estimates of smaller work components will be made. These will confirm earlier broad estimates.

## Slide 10: Problems with over and under estimates
An over-estimate is likely to cause project to take longer than it would otherwise.
This can be explained by the application of two laws :
  Parkinson’s Law: ‘Work expands to fill the time available’
    Over estimating the duration required to complete a target will cause staff to work less hard in order to fill the available time .
  Brook’s Law : Putting more people on a late job makes it later
    If there is an over estimate of the total people required, this could lead to more staff being allocated than the actual need. And as the project team grows in size, more effort will be required for management, coordination and communication.

## Slide 11: Problems with over and under estimates
Under-estimating a project
  Can cause the project to not be delivered on time or cost
  But still could be delivered faster than a more generous estimate
On the other side the danger of underestimating a project is the effect on the quality.
  Staff, particularly those with less experience, could response to pressing deadlines by producing substandard work.
  Substandard work might only become visible at the later (testing) phases of a project, where extensive re-work can easily delay project completion.
  Motivation is also decreased when targets are always unachievable.

## Slide 12: Activity 1
Calculate the productivity (SLOC / work per month) of each of the projects and also for the organization as a whole. If the project leaders for projects a and d had correctly estimated the SLOC and then used the average productivity of the organization to calculate the effort needed to complete the projects, how far would their estimates have been from the actual effort?

## Slide 13: Activity 1
Project | Effort (pm) | SLOC
A | 16.7 | 6050
B | 22.6 | 8363
C | 32.2 | 13334
D | 3.9 | 5942
E | 17.3 | 3315
F | 67.7 | 38988
G | 10.1 | 38614
H | 19.3 | 12762
I | 59.5 | 26500

## Slide 14: Basis for software Effort Estimation
The need for historical data
Parameters to be estimated
Measure of work
Measure of effort

## Slide 15: The need for historical data
Most estimating methods need information about past projects.
Care has to be considered when applying past performance to new projects because of possible differences in factors such as :
  Different programming languages
  Different experience of staff
There are international Data Base containing data about thousands of projects that can be used as reference.
Notes: ISBSG international software benchmarking standards group….4800 projects

## Slide 16: Parameters to be estimated
Two project parameters are to be estimated for carrying out project planning.
  Duration: It is usually measured in months,
  Effort: Popular unit for effort measurement is person-month (pm)
One pm is the effort an individual can typically put in a month.
Notes: Losses due to holidays, weekly offs are considered while estimating pm.

## Slide 17: Measure of Work
Work can be measured in terms of cost required in accomplishing the project and the time over which it is to be completed.
Direct calculation of time and cost to implement software is difficult in early stages as they both depend on :
  The developer’s capability and experience
  The technology that will be used

## Slide 18: Measure of Work
It is therefore a standard practice to first estimate the project size, and by using it, the effort and time taken to develop the software can be computed.
At present, two metrics are being popularly used to measure size
  Source lines of code (SLOC)
  Function point (FP)

## Slide 19: Measure of effort
Person-month (pm) is a popular unit for effort estimation.
It quantifies the effort that can be put in by one person over one month.
Effort that has been put in by a team can be measured in units of pm based on the number of persons deployed and the number of months that they have worked.

## Slide 20: Software effort estimation techniques
Parkinson: Staff effort available to do the project becomes the estimate.
Price to win: Here the estimate is a figure that seems sufficiently low to win a contract.
Expert judgment: Based on the advice of knowledgeable staff.

## Slide 21: Software effort estimation techniques
Analogy: A similar completed project is identified and its actual effort is used as the basis of the estimate.
Bottom-up: Component tasks are identified and estimated and these individual estimates are aggregated.
Top-down: An over all estimate for the whole project is broken down into the effort required for component tasks.

## Slide 22: Expert Judgment
It involves asking for an estimate of task effort from someone who is knowledgeable either about the application or the development environment.
This method is often used when an existing piece of software is needed to change.
The estimator examine the existing code in order to judge the proportion of code affected and from that derive an estimate.
Some one familiar with the software would be in the best position to do that.

## Slide 23: Estimation by Analogy
For a new project the estimator identifies the previous completed projects that have similar characteristics to it .
The new project is referred to as the target project or target case.
The completed projects are referred to as the source projects or source case.
The effort recorded for the matching source case is used as the base estimate for the target project.
The estimator calculates an estimate for the new project by adjusting the ( base estimate ) based on the differences that exist between the two projects.

## Slide 24: Estimation by Analogy
There are software tools that automate this process by selecting the nearest project cases to the new project .
Some software tools perform that by measuring the Euclidean distance between projects.
The Euclidean distance is calculated as follows :
Distance = square-root of (( target_parameter1-source_parameter1)2 +….+ ( target_parameter n - source_parameter n ) 2 )

## Slide 25: Estimation by Analogy
Assume that cases are matched on the basis of two parameters , the number of inputs and the number of outputs .
  The new project ( target case ) requires 7 inputs and 15 output
You are looking into two past cases or source cases to find a better analogy with the target project :
  Project A : has 8 inputs and 17 outputs .
  Project B : has 5 inputs and 10 outputs .
Which is a more closer match for the new project A or project B ?

## Slide 26: Estimation by Analogy
Distance between new project and project A :
  Square-root of (( 7-8 ) 2 + ( 15-17 ) 2 )= 2.24
Distance between new project and project B:
  Square-root of (( 7-5 ) 2 + ( 15-10 ) 2 )= 5.39
Project A is a better match because it has less distance than project B to the new project.

## Slide 27: Activity 2
There is a new project, that is known to require 7 inputs and 15 outputs. There are two past cases: project A has 8 inputs and 17 outputs and project B has 5 inputs and 10 outputs. Which of the source projects have better analogy with the target new project?

## Slide 28: Bottom-up Estimation
Break the project into smaller and smaller components.
Stop when you get to what one person can do in one/two weeks.
Estimate costs for the lowest level activities.
At each higher level calculate estimate by adding estimates for lower levels.
When a project is completely novel or there is no historical data available, bottom-up approach would be the perfect choice.

## Slide 29: Bottom-up Estimation
Following are the steps how a bottom up approach can be used for estimating effort
  Think about the number and types of software modules in the final system.
  Estimate the SLOC of each identified module.
  Estimate the work content, taking into account complexity.
  Calculate the work days effort.

## Slide 30: Top Down Estimation
Most commonly used top down estimation approaches are Function Points Mark II and COCOMO II.

## Slide 31: Function Points Mark II
The function point is a "unit of measurement" to express the amount of business functionality an information system provides to a user.
It is a process which defines the required functions and their complexity in a piece of software in order to estimate the software's size upon completion.
The Mark II Method was defined by Charles Symons in 1991.

## Slide 32: Function Points Mark II
FP Mark II measures the size in FPs.
The size is initially measured in unadjusted function points (UFPs) to which a technical complexity adjustment can then be applied (TCA).

## Slide 33: Function Points Mark II
The assumption here is that an information system comprises transactions that have the basic structure shown in Figure

## Slide 34: Function Points Mark II
For each transaction FPs are calculated as
FP = Wi * (number of input data element types) +
We * (number of entity types referenced) +
Wo * (number of output data element types)

## Slide 35: Function Points Mark II
Wi, We, Wo are weightings derived by asking developers the proportions of effort spent in previous projects developing the code dealing with Inputs, accessing and modifying stored data and Processing outputs.
The process for calculating weightings is time consuming and most FP counters use industry averages which are currently 0.58 for Wi, 1.66 for We and 0.26 for Wo.

## Slide 36: Function Points Mark II
Tables have been calculated to convert the FPs to lines of code for various languages. For example it is suggested that 53 lines of Java are needed on average to implement one FP, while for Visual C++ the figure is 34.

## Slide 37: Activity 3
A cash receipt transaction system accesses two entity types (INVOICE and CASH RECEIPT). The data inputs are (Invoice number, data received and cash received). If an invoice record is not found for the invoice number then an error message is issued. If the invoice number is found then a CASH RECEIPT record is created. Thus the error message is the only output of transaction. Calculate the function points.
Also calculate the SLOC, if the system is to be implemented in Java.

## Slide 38: COCOMO II: A Parametric Productivity Model
COCOMO II is a parametric productivity model.
Barry W. Boehm’s COCOMO (Constructive Cost MOdel) actually refers to a group of models.
Boehm presented his first model (COCOMO 81) in late 1970s based on a study of 63 projects.
This basic model was built around the equation
Effort = c (size)k

## Slide 39: COCOMO II: A Parametric Productivity Model
Effort was measured in pm, size was measured in kdsi, and c and k were constants.
The first step was to derive an estimate of the system size in terms of kdsi. The constants c and k depend on whether the system could be classified as organic, semi-detached or embedded.
System Type | C | k
Organic | 2.4 | 1.05
Semi-detached | 3.0 | 1.12
Embedded | 3.6 | 1.20
Notes: Kilo delivered source instruction.

## Slide 40: COCOMO II: A Parametric Productivity Model
Organic Mode: This would typically be the case when relatively small teams develop software in a highly familiar in-house environment, system being developed is small and interface requirements are flexible.
Embedded Mode: Product being developed had to operate within very tight constraints and changes to the system are very costly.
Semi-detached Mode: This combined elements of the organic and the embedded modes or have characteristics that came between the two.

## Slide 41: COCOMO II: A Parametric Productivity Model
Over years, Barry Boehm and his co-workers have refined a family of cost estimation models of which the latest one is COCOMO II (developed in 1995, published in 2000).
It uses various multipliers and exponents, values of which have been set initially by experts.
A database containing the performance details of executed projects has been built up and is periodically analyzed so that the expert judgements can be progressively replaced by the values derived from actual projects.

## Slide 42: COCOMO II: A Parametric Productivity Model
Effort is calculated as
Pm = A (size) (sf) *(em1) * (em2) * ….. * (emn)
A is a constant (2.94), size is measured in kdsi and sf is the exponent scale factor calculated as
Sf = B + 0.01 * ∑ (exponent driver ratings)
B is a constant currently set at 0.91.

## Slide 43: COCOMO II: A Parametric Productivity Model
The qualities that govern the exponent drivers are
Precedentedness (PREC): This quality is the degree to which there are precedents or similar past cases for the current project. The greater the novelty of the new system, the more uncertainty there is and higher the value given to the exponent driver .

## Slide 44: COCOMO II: A Parametric Productivity Model
Development Flexibility (FLEX): This reflects the number of different ways there are of meeting the requirements. The less flexibility there is, the higher the value of exponent driver.
Risk Resolution (RESL): This reflects the degree of uncertainty about the requirements. If they are liable to change then a high value would be given to this exponent driver.

## Slide 45: COCOMO II: A Parametric Productivity Model
Team Cohesion (TEAM): This reflects the degree to which there is a large dispersed team as opposed to there being a small tightly knit team.
Process Maturity (PMAT): The more structured and organized the way the software is produced, the lower the uncertainty and lower the rating for this exponent driver.

## Slide 46: COCOMO II: A Parametric Productivity Model
Each of the scale factors for a project is rated according to a range of judgements: very low, low, nominal, high, very high and extra high. There is a number related to each rating of the individual scale factors.

## Slide 47: COCOMO II: A Parametric Productivity Model

## Slide 48: Activity 4
A new project has average novelty for the software supplier who is going to execute it and is thus given a nominal rating on this account for precedentedness. Development flexibility is high, but requirements may change radically and so the risk resolution exponent is rated very low. The development team are all located in the same office and this leads to team cohesion being rated as very high, but the software house as a whole tends to be very informal in its standards and procedures and the process maturity driver has therefore been given a rating of low.
  What would be the scale factor (sf) in this case?
  What would be the estimate of effort, if the size of the application was estimated as 2000 LOC.

## Slide 49: Cost Estimation
Project cost can be obtained by multiplying the estimated effort with the man-power cost per month.
Activity 5: Assume that the size of an organic type software product is estimated to be 32,000 lines of source code. Assume that the average salary of a software developer is $2,000 per month. Determine the amount of staff cost to develop the product.
Notes: This cost is only the manpower cost. Overhead costs should also be added.

## Slide 50: Reading
[Chapter#5] “Software Project Management by Bob Hughes and Mike Cotterell, McGraw-Hill Education; 6th Edition (2009). ISBN-10: 0077122798”.