## Slide 1: RESOURCE ALLOCATION

## Slide 2: Contents
Introduction
Nature of Resources
Identifying Resource Requirements
Scheduling Resources
How to allocate individuals to tasks???
Cost schedules

## Slide 3: Introduction
Up till now we have learned
  To identify the total number of activities.
  To use activity network analysis techniques to plan when activities should take place.
  To use the PERT technique to forecast a range of expected dates by which activities would be completed by considering risks.
  In both cases, plans took no account of availability of resources

## Slide 4: Introduction
When we allocate resources to the identified activities, the process is considered as resource allocation.
The allocation of resources to activities will lead to:
  A review of the ideal activity plan.
  Modification of the ideal activity plan.

## Slide 5: Nature of Resources
Resources can be:
  Item required for the execution of the project.
  Person required for the execution of the project.
Some resources will be required for a specific period (e.g. a specific software developer).
Some resources will be required for the whole duration of the project (e.g. project manager)

## Slide 6: Nature of Resources
In general, resources will fall into one of seven categories
  Labor
  Equipment
  Materials
  Space
  Services
  Time
  Money

## Slide 7: Identifying Resource Requirement
The first step in producing a resource allocation plan is to list the resources that will be required along with the expected level of demand.
This will normally be done by considering each activity in turn and identifying the resources required.

## Slide 8: Identifying Resource Requirement
But there could be resources that are not activity specific and are either
  A part of the project infrastructure such as project manager.
  Or
  Resources required to support other resources. Office space for example might be required to house contract software developers.

## Slide 9: Identifying Resource Requirement
Consider following data
Activity | Estimated Duration (days) | Activity | Estimated Duration (days)
Specify overall system | 34 | Design module C | 4
Specify module A | 20 | Design module D | 4
Specify module B | 15 | Code/test module A | 30
Specify module C | 25 | Code/test module B | 28
Specify module D | 15 | Code/test module C | 15
Check Specification | 2 | Code/test module D | 25
Design module A | 7 | System integration | 6
Design module B | 6 |  | 

## Slide 10: Identifying Resource Requirement

## Slide 11: Identifying Resource Requirement

## Slide 12: Allocating Resources
Allocating a recourse (a member of the project team) to an activity limits the flexibility for resource allocation and scheduling of other activities.
  Since each activity has a start and an end date this team member will not be available for the other activities for that period.
It is therefore helpful to prioritize the activities so that resources can be allocated to competing activities in some rational order.
The priority must always be to allocate resources to critical path activities and then to those activities that are most likely to affect others.

## Slide 13: Allocating Resources
Two approaches of prioritizing activities are
  Total Float Priority
  Ordered List Priority
Total Float Priority
  Activities with the smallest total float are given highest priority.
  Thus Activities are allocated resources in ascending order of total float.
  It is desirable to recalculate floats as the scheduling proceeds. Why?

## Slide 14: Allocating Resources
Ordered List Priority: Activities that can proceed at the same time are ordered according to a set of simple criteria. An example of this is Burman’s priority list which takes into account activity duration as well as total float.
  Shortest critical activity.
  Critical activities.
  Shortest non‐critical activity.
  Non‐critical activity with least float.
  Non‐critical activities.

## Slide 15: Allocating Resources
Example:
  This example will demonstrate that why there arise some need to change the activity network plan by considering the
    availability of resources
    effective utilization of resources

## Slide 16: Allocating Resources
Look at the Activity Plan in slide 10
  Instead of having 4 (analyst/designer), we have only 3. Therefore we need to revise it according to the resource availability.
  Resources are also not being effectively utilized as
    Two of the analyst/designers stay idle for 12 days. (from 49 to 61)
    One stays idle for 7 days. (from 54 to 61)
    One stays idle for 2 days. (from 59 to 61).

## Slide 17: Allocating Resources
It is apparent that
  Specification of all four modules cannot be done in parallel as there are only three analysts/designers.
  The activity of checking all the specifications together, before allowing design to start is causing a significant bottleneck, as analyst/designer of modules A, B and D are doing nothing in order to wait for the completion of Module C specification.
Both points are causing a delay in the over all project duration. This situation is solved by redrawing the precedence network.

## Slide 18: Allocating Resources

## Slide 19: Allocating Resources

## Slide 20: How to allocate individuals to tasks???
In allocating individuals to the tasks, a number of factors need to be taken into account.
Availability
  Whether a particular individual will be available when needed.
  Investigate the risks that can prevent that from happening.
Criticality
  Allocating more experienced personnel to critical activities often:
    Shortens the project duration
    reduces the risk of overrun.

## Slide 21: How to allocate individuals to tasks???
Risk
  Allocating the most experienced staff to the highest‐risk activities is likely to have the greatest effect in reducing overall project uncertainties.
Training
  Allocate junior staff to appropriate non critical activities, so there will be enough slack for them to train and develop skills.
Team Building
  The selection of individuals in the project team must take account of
    the final shape of the project team
    the way they will work together.

## Slide 22: Cost Schedules
After allocating resources, it is now time to produce a detailed cost schedule showing weekly or monthly costs over the life of the project.
Calculation of cost is straightforward where organization has standard cost figures for staff and other resources.
When this is not the case, then project manager have to put effort in calculating cost.

## Slide 23: Cost Schedules
In general, costs are categorized as follows
  Staff costs
  Overheads
  Usage charges
Activity 2: Estimated duration of a given project is 100 days. Overheads are recovered by charging a fix $200 per day against project. Staff costs are given in the table. Project manager has spent an additional 10 days planning the project and carrying out the post project review. Calculate the total costs of the project.

## Slide 24: Cost Schedules
Staff Members | Daily Cost ($) | Days required
Project Manager | 300 | Whole Duration
Employee 1 | 250 | 50
Employee 2 | 175 | 25
Employee 3 | 225 | 27
Employee 4 | 150 | 30
Employee 5 | 150 | 28
Employee 6 | 150 | 15
Employee 7 | 150 | 25

## Slide 25: Reading
[Chapter#8]“Software Project Management by Bob Hughes and Mike Cotterell, McGraw-Hill Education; 6th Edition (2009). ISBN-10: 0077122798”