## Slide 1: MONITORING AND CONTROL

## Slide 2: Contents
Introduction
Creating the Framework
Review
Visualizing Progress
Getting the Project Back to Target
Change Control
Software Configuration Management

## Slide 3: Introduction
Up till now, we have learnt how to make a schedule.
Once a schedule is published and project is started, attention now should be on progress.
This requires
  Monitoring of what is happening.
  Comparison of actual achievement against the schedule.
  If required, then revision of schedule to bring the project back to target.

## Slide 4: Creating the Framework
Regular monitoring involves
  Finding out what is happening
  Comparing it with targets
  Ensuring that targets are met
  Exercising control
If there may be a mismatch between the planned outcomes and the actual ones, then for bringing the project back to the target
  Re planning can be done
  Target could be revised

## Slide 5: Project Control Cycle
Figure on the next slide illustrates a model of the project control cycle and shows how, once the initial project plan has been published, project control is a continual process of
  Monitoring progress against the plan
  Revising the plan to take account of deviations

## Slide 7: Project Control Cycle
In practice, we are normally concerned with four types of shortfalls
  Delays in meeting target dates
  Shortfall in quality
  Inadequate functionality
  Cost overrun
In this chapter, we are mainly concerned with the first and the last one.

## Slide 8: Project Control Cycle
Responsibility:
  The overall responsibility for ensuring satisfactory progress is often the role of project steering committee and management board.
  Day to day responsibility will rest with the project manager.
  In the case of larger projects, some of project manager’s duty can be delegated to team leaders.

## Slide 9: Project Control Cycle
Steering Committee
Project Manager
Team Leader
Team Leader
Analysis/design Team
Programming Team
Team Leader
Team Leader
User Documentation Team
Quality Control Team

## Slide 10: Project Control Cycle
Information required for assessing Progress
  Information used to assess the project can either be collected routinely or triggered by specific events.
  This information should be objective and tangible.

## Slide 11: Project Control Cycle
Setting Checkpoints
  It is essential to set a series of checkpoints in the initial activity plan.
  Checkpoints may be
    Regular (monthly)
    Tied to specific events (production of a report)

## Slide 12: Project Control Cycle
Taking snapshots
  The frequency of progress reports will depend upon the size and degree of risk of the project.
  Team leaders, may want to assess progress daily where as project managers may find weekly reporting appropriate.
  In general, higher the level, less frequent and less detailed the reporting needs to be.

## Slide 13: Activity 1
A software developer has written the first 250 lines of a java program that is estimated to require 500 lines of code. Explain why it would be unreasonable to assume that the programming task is 50% complete.

## Slide 14: Collecting and Assessing the Data
For project monitoring, it is necessary
  To gather information about partially completed activities.
  To make a forecast of how much work is left to be completed.
It is a bit difficult to make such forecasts accurately.
One popular way of making such forecasts is Red/Amber/Green (RAG) Reporting.

## Slide 15: Collecting the Data
In RAG reporting, the likelihood of meeting the planned target date is estimated.
It consists of following steps
  Identify the key (first level) elements for assessment in a piece of work.
  Break these key elements into constituent (second level) elements.

## Slide 16: Collecting the Data
  Assess each of the second level elements on the scale green for on target, amber for not on target but recoverable, and red for not on target and recoverable only with difficulty.
  Review all the second level assessments to arrive at first level assessments.
  Review first and second level assessments to produce an overall assessment.

## Slide 17: Collecting the Data

## Slide 18: Collecting the Data
Following completion of assessment forms for all activities, the project manager uses these as a basis for evaluating the overall status of the project.
Any critical activity classified as amber or red will require further consideration and often leads to a revision of the project schedule.
Non-critical activities are likely to be considered as a problem if they are classified as red, especially if all their float is likely to be consumed.

## Slide 19: Review
Review of a work product is another important mechanism for
  Monitoring the progress of project
  Ensuring the quality of the work products
Review techniques have become extremely popular being a cost effective defect removal mechanism.

## Slide 20: Advantages of Review
It helps to identify any deviation from standards, including issues that might affect maintenance of the software.
Reviewers suggest ways to improve the work products.
In addition to defect identification, a review meeting often provides learning opportunities to all the participants of review meeting. The lessons acquired from the review meeting allow them to avoid committing similar defects in future.
The review participants gain a good understanding of the work product under review, making it easier for them to interface or use the work product in their work.

## Slide 21: Review Roles
In every review meeting, a few key roles need to be assigned to the review team members. These roles are
  Moderator
  Recorder
  Reviewer

## Slide 22: Review Roles
Moderator schedule meetings, distribute review material, lead and moderate review sessions, ensure the defects are tracked to closure.
Recorder records the defects found, the time and the effort data.
Reviewers review the work product and give specific suggestions to the author about the existing defects and also point out ways to improve the work product.

## Slide 23: Review Process
Review of any work product consists of the following four activities
  Planning
  Review Preparation and Overview
  Review Meeting
  Rework and Follow-up

## Slide 24: Review Process
Planning
Preparation
Review Meeting
Rework and Follow-Up

## Slide 25: Review Process
Planning:
  When the author of a work product is ready for submitting his work for review, the project manager nominates a moderator.
  Moderator can be some one familiar with the product.
  Besides moderator, some other members are also nominated for review team.
  Review process works best when the number of members is between 5 and 7.

## Slide 26: Review Process
Preparation:
  To initiate the review process, the moderator organize a brief preparation meeting.
  Copies of the work product are distributed to the review team members.
  Author presents a brief overview of the work product.
  Moderator highlights the objectives of the review.
  Reviewers, then individually carry out review and record their observations in separate documents called review logs.

## Slide 27: Review Process
Review Meeting:
  Reviewers give their comments based on their individual review logs.
  The comments may pertain to a defect, work simplification, maintainability etc.
  Author responds to the reviewer comments.
  Moderator ensures that the discussion remains focused and productive.
  Recorder scribes all the defects and points that the author agrees to in the form of a review log.

## Slide 28: Review Process
Rework and Follow-Up:
  Author addresses all the issues raised by the reviewers by carrying out the necessary modifications.
  The corrected work product is circulated among review team.
  A final brief meeting is conducted to check whether all the issues have been resolved satisfactorily.
  A final summary report of the review is prepared.

## Slide 29: Visualizing Progress
Once the data about the project progress is collected, there arises the need of representing it to greatest effect. This can be done by
  Gantt Chart
  Timeline

## Slide 30: Visualizing Progress (Gantt Chart)

## Slide 31: Visualizing Progress (Timeline)

## Slide 32: Getting the Project Back to Target
Almost all projects are subjected to delays and unexpected events.
It is the task of project manager to recognize when this is happening and mitigate the effects with minimum delay and disruption to the project team.
Two main strategies are considered while re planning to bring a project back to the target.
  Shorten the Critical path
  Alter activity precedence requirement

## Slide 33: Shortening the Critical Path
Overall duration of the project is determined by the current critical path, therefore it can be shortened to bring forward a project completion date.
This shortening of critical path can be done by
  Adding resources
  Increase use of current resources
  Reallocate staff to critical activities
  Reduce scope
  Reduce quality

## Slide 34: Altering the Precedence Requirements
If shortening of critical activities proves insufficient, next step is to consider the constraints by which some activities have to be delayed in order to wait for completion of others.
The original project network would have been drawn up assuming ideal conditions and normal working practices.
However to avoid late delivery of project, it is now worth questioning whether yet un started activities really do have to wait the completion of others.

## Slide 35: Altering the Precedence Requirements
For example in any organization it is normal to complete system testing before commencing user training, but in order to avoid late completion it might be considered acceptable to start training earlier.
Another way to overcome precedence constraints is to subdivide an activity into a component that can start immediately and one that is still constrained as before.

## Slide 36: Change Control procedure
Change control is an important part of the project management.
While change may help ensure the project's alignment with business needs, it is important to consider and approve each change carefully.
The change control process in project management ensures that each change proposed during a project is adequately defined, reviewed and approved before implementation.
The change control process helps avoid unnecessary changes.

## Slide 37: Change Control procedure
Change control contains five stages:
  Proposing a Change
  Summary of Impact
  Decision
  Implementing a Change
  Closing a Change
There are two documents used during the process:
  Change Log: used to provide a record of all changes requested and decisions made
  Change Request Form: used to document details of the change, including the business case

## Slide 38: Change Control procedure
Proposing a Change
  This process gives the ability for anyone in the project team (including the customer) to suggest a change to the project.
  The proposal must include a description of the change and expected benefits or other reason for the change.
  The change is presented using the Change Request Form and added to the Change Log for the project.

## Slide 39: Change Control procedure
Summary of Impact: This process is carried out by the project manager, who will consider the overall effect on the project, covering the following items:
  Quantifiable cost savings and benefits
  Legal, regulatory or other unquantifiable reason for change
  Estimated cost of the change
  Impact on timescales
  Extra resources needed
  Impact on other projects and business activities
  New risks and issues
After this assessment, the project manager recommends whether to carry out the change.

## Slide 40: Change Control procedure
Decision: This process involves a review of the change request by an approved authority who will consider all the information provided by the project manager and person making the request. The decision will usually be:
  Accept
  Accept with comments and special conditions
  Reject
  Defer (change is not approved, but is left for consideration later)

## Slide 41: Change Control procedure
Implementing a Change
  If the change is approved it is planned, scheduled and executed at a time agreed with the stakeholders.
  As part of the planning, a regression test plan is needed in case the change needs to be backed out.
  After implementation, it is usual to carry out a post-implementation review.
Closing a Change
  Once implemented, the requester checks and agrees on the change, and it is closed in the Change Log by the project manager.

## Slide 42: Activity 2
A change in a program specification will normally be carried out through changes to the program design and then code. What other products might need to be modified?

## Slide 43: Software Configuration Management (SCM)
In a software development environment, all work products (code, design document etc.) get modified as development activities are carried out.
Thus the state of all work products continually change during development phase.
The state of all work products at any point of time is called configuration of the software product.

## Slide 44: Software Configuration Management (SCM)
Software configuration management is a process that runs parallel with development phase to effectively track and control the configuration of a software product during its entire life cycle.

## Slide 45: Software Configuration Management (SCM)
Before the discussion of configuration management, some basic terms should be defined
  Configuration: State or condition of all work products at any point of time is called the configuration of the software product.
  Configuration Item: A work product under configuration control is called configuration item.

## Slide 46: Software Configuration Management (SCM)
  Version: Configuration of a software product keeps changing because of development and maintenance activities. Version is basically a particular configuration that existed at certain point in time. Versioning is technically a number scheme that helps us identify a specific configuration at a certain point in time.

## Slide 47: Software Configuration Management (SCM)
  Baseline: it is a software configuration that has been formally reviewed and agreed upon, and serves as a basis for further development.
  Variant: variants are versions that are intended to coexist. Different variants may be needed to run the software on different operating systems or on different hardware platforms

## Slide 48: Software Configuration Management (SCM)
Configuration management is carried out through the following two principle activities.
  Configuration identification
  Configuration control

## Slide 49: Software Configuration Management (SCM)
Configuration identification involves deciding which work products should be kept under configuration management.
Work products associated with a software development process are categorized into three main categories
  Controlled
  Pre-controlled
  Uncontrolled

## Slide 50: Software Configuration Management (SCM)
Configuration control allows only authorized members to access controlled objects and prevents unauthorized changes.
In order to change a controlled work product, a developer gets a private copy of that product through a reserve operation.
Configuration management tool allow only one team member to reserve a product at any time, thus solving the problem of concurrent access.

## Slide 51: Software Configuration Management (SCM)
Following is the procedure to modify a work product under configuration control
  If a developer need to change a work product, he will first make a reserve request.
  A reserve request by a team member is honored only if appropriate authorization has been given by the project manager to that member for that specific work product.

## Slide 52: Software Configuration Management (SCM)
  After successful execution of reserve command, a private copy of work product will be created in the local directory of developer.
  He will then carry out all required changes to the work product in his private copy.
  After completion of all necessary changes, the changes are restored in configuration management repository.

## Slide 53: Software Configuration Management (SCM)
  Restoring the changed work product to the system configuration requires the permission of a change control board (CCB).
  The CCB usually consists of the project manager, development team members and some representative of upper management.

## Slide 54: Software Configuration Management (SCM)
Following are some benefits of using a proper configuration management system
  Solving problems associated with concurrent access
  Ease in Undoing changes
  System accounting
  Handling versions
  Preventing unauthorized access to the work products

## Slide 55: Activity 3
What are the disadvantages of putting too much or too little of work products under configuration control?

## Slide 56: Release Management
Release management oversees all the stages involved in a software release from development and testing to deployment.
Release management is required anytime a new product or even changes to an existing product are requested.

## Slide 57: Release Management
There are five primary steps of release management
  Plan release
  Build release
  User acceptance testing
  Prepare release
  Deploy release

## Slide 58: Readings
[Chapter 9]“Software Project Management by Bob Hughes and Mike Cotterell, McGraw-Hill Education; 6th Edition (2009). ISBN-10: 0077122798”
https://www.projectsart.co.uk/what-is-change-control.php
https://www.lucidchart.com/blog/release-management-process