## Slide 1: Identification of Problem (Area mapping)
Understanding the causes and effects of the social problem

## Slide 2: Problem Tree
The problem tree is a useful tool for analyzing a problem with all its causes, effects and factors.
A problem tree can be created in the space of a few hours to a day. All relevant internal and external stakeholders should be involved.
How you can transform this problem tree into a solution tree that is useful in defining your project’s approach and objectives.

## Slide 4: Step 1: Define the core problem
The core problem should be formulated from the perspective of the target group and should take the form of a negative statement.
As an example, "High levels of unemployment among young people" is indeed a negative, but is not specific enough

## Slide 5: Step 2: Identify causes and effects
As a second step, you’ll work out the causes and effects of the core problem. In this process, individual causes and effects should be expressed as negative statements.
Examples might include "youths do not have sufficient social skills", "too few spots in vocational-training programs within the region," "lack of future prospects," or "strong willingness to engage in violence"

## Slide 6: Needs assessment and context analysis
Was the problem deﬁned clearly?
Are the causes of the problem entirely clear?
Are the effects of the problem clear?
Are the scope and size of the problem clear?
Is the target group clear?
Has the target group’s situation been fully understood?

## Slide 7: Continue….
Have the needs of the target group been fully understood?
Have the problem and the target group’s needs been understood well enough to provide a basis for the project’s development?
Have the lessons learned from other programs been utilized?
Were gaps in existing support programs identiﬁed?

## Slide 8: Continue….
The problem, objective and strategy tree analysis is one participatory tool of mapping out main problems, along with their causes and effects, supporting project planners to identify clear and manageable goals and the strategy of how to achieve them.
There are three stages in this analytic process:
(1) the identification of the negative aspects of an existing situation with their “causes and effects” in a problem tree,
(2) the inversion of the problems into objectives leading into an objective tree,
(3) the decision of the scope of the project in an analysis of strategies.

## Slide 9: Continue…
A properly planned project is addressing the real needs of the beneficiaries and is therefore based upon a correct and complete analysis of the existing situation. The existing situation should be interpreted according to the views, needs, interests and activities of parties concerned.
It is essential that all those involved participants accept the plans and are committed to implement them. The problem tree analysis belongs to the family of participatory planning techniques, in which all parties involved identify and analyse the needs together, creating ownership and commitment among the involved parties (e.g. beneficiaries, implementing organisations, local governments).
The problem tree, together with the objective tree and analysis of strategies, is a methodology of three steps for identifying main problems, along with their causes and effects, helping project planners to formulate clear and manageable objectives and the strategies of how to achieve them.

## Slide 10: Advantages
The problem can be broken down into manageable and definable chunks. This enables a clearer prioritization of factors and helps focus objectives
There is a better understanding of the problem and its often interconnected and even contradictory causes. This is often the first step in finding win-win solutions
It identifies the constituent issues and arguments, and can help establish who and what the political actors and processes are at each stage
It can help establish whether further information, evidence or resources are required to make a strong case, or build a convincing solution
Present issues - rather than apparent, future or past issues - are dealt with and identified
The process of analysis often helps build a shared sense of understanding, purpose and action

## Slide 11: Disadvantages
It may be difficult to understand all effects and causes of a problem right from the beginning
Requires time to bring all relevant actors together and to discuss the problems of their water and sanitation system

## Slide 12: Step 1: Problem Analysis
The problem analysis is the phase in which the negative aspects of a given situation are identified, establishing the cause and effect relationship between the observed problems. The problem analysis is of prime importance with regard to project planning, since it strongly influences the design of all possible interventions (MDF 2005). The problem analysis includes (EC 2004):
Definition of the framework and the subject of analysis.
Identification of problems faced by target groups and beneficiaries.
Visualization of the problems in form of a diagram, called “problem tree” to help analyze and clarify cause-effect relationships.

## Slide 13: Step 2: Objectives Analysis
Analysis of objectives is a methodological approach employed to describe the situation in the future once identified problems have been remedied, depicting the ends and the means in a diagram called “objective tree”.
he negative situations of the problem tree are converted into solutions, expressed as “positive achievements”. For instance, in the shown example of river pollution, “river water quality is deteriorating” is converted into “quality of river water is improved”. These positive achievements are in fact objectives and are presented in an objective tree showing the means/ends hierarchy.
Since the negative situations of the problem tree have to be reformulated into positive situations that are desirable and realistically achievable, it is of primal importance that all stakeholders are involved in the discussions giving their feedback

## Slide 14: Step 3: Analysis of Strategy
After having decided about the desired future situation, possible interventions must be selected in order to determine the scope of the project, i.e. what should/can be included within the project.
This analytical stage is the most difficult and challenging, as it involves synthesizing a significant amount of information and making a complex judgement about the best implementation strategy to pursue.
In practice a balance has to be found to deal with the different stakeholders' interests, political demands and practical constraints. However, the potential merits and difficulties associated with addressing problems in different ways have to be fully scrutinized before any detailed design work is undertaken