## Slide 1: Risk Management in Software Projects

## Slide 2: What We will cover today
Risk
Types of risks and their examples
The risk management process.
Flow of processes in risk management.

## Slide 3: Risk management
Risk management is concerned with identifying risks and drawing up plans to minimise their effect on a project.
A risk is a probability that some adverse circumstance will occur
  Project risks affect schedule or resources;
  Product risks affect the quality or performance of the software being developed;
  Business risks affect the organisation developing or procuring the software.

## Slide 4: Software risks
Risk | Affects | Description
Staff Turnover | Project | Experienced staff will leave the project during development
Management Change | Project | There is a change of Organizational management with different priorities.
Hardware Unavailability | Project | Hardware that is essential for the project will not be delivered in schedule
Requirements change | Project and product | There will be large number of changes to the requirements than anticipated.
Specification delays | Project and product | Specification of essential interfaces are not available on schedule

## Slide 5: Software Risks……
Risk | Affects | Description
Technology change | Business | The underlying technology in which the system is built is superseded by new technology
Product Competition | Business | A competitive product is marketed before the system is completed.

## Slide 6: The risk management process
Risk identification
  Identify project, product and business risks;
Risk analysis
  Assess the likelihood and consequences of these risks;
Risk planning
  Draw up plans to avoid or minimise the effects of the risk;
Risk monitoring
  Monitor the risks throughout the project;

## Slide 7: The risk management process

## Slide 8: Risk identification
Some types of risks are
Technology risks.
People risks.
Organisational risks.
Requirements risks.
Estimation risks.

## Slide 9: Risk types
Risk type | Possible risks
Technology | The databases used in the system cannot process as many transactions as expected. Irctc website suffers this risk…..
People | It is impossible to recruit staff with skills required. Key staff is ill and is unavailable at critical times. E.g if some very innovative project is taken by the company
Organizational | Organization is restructured so that different management is responsible for the project. Organizational financial problems force reduction in the budget.

## Slide 10
Risk type | Possible risks
Requirements | Changes in requirement that require major design rework are proposed. Customers fail to understand the impact of requirement changes.
Estimation | The time required to develop software is underestimated. The rate of defect repair is underestimated. The size of software in underestimated.
Risk types

## Slide 11: Risk analysis
Assess probability and seriousness of each risk.
Probability may be very low, low, moderate, high or very high.
Risk effects might be catastrophic, serious, tolerable or insignificant.

## Slide 12: Risk analysis (i)
Risk | Probability | Effect
Organizational financial problems force reduction in the project budget. | Low | Catastrophic
It is impossible to recruit staff with skills required for the project. | High | Catastrophic
Key staff are ill at critical times in the project. | Moderate | Serious
Changes in requirement that require major design rework are proposed | Moderate | Serious
The organization is restructured so that different management are responsible for the project. | High | Serious

## Slide 13: Risk analysis (ii)
Risk | Probability | Effects
The database used in the project cannot process as many transactions per second as expected. | Moderate | Serious
The time required to develop software is underestimated. | High | Serious
Customers fail to understand the impact of requirements change | Moderate | Tolerable
Required Training for staff is not available | Moderate | Tolerable
The size of software is underestimated | High | Tolerable

## Slide 14: Risk planning
Consider each risk and develop a strategy to manage that risk.
Three common strategies are used
Avoidance strategies
  The probability that the risk will arise is reduced;
Minimisation strategies
  The impact of the risk on the project or product will be reduced;
Contingency plans
  If the risk arises, contingency plans are plans to deal with that risk;

## Slide 15: Risk management strategies (i)
Risk | Strategy
Organizational Financial Problems | Prepare a brief document for senior management showing how project is making a very important contribution to goals of the business.
Recruitment problems | Alert customer of potential difficulties and the possibility of delays, investigate buying-in components.
Staff illness | Reorganize team so that there is more overlap of work and people therefore understand each others jobs.
Defective components | Replace potentially defective components with bought in components of known reliability

## Slide 16: Risk management strategies (ii)
Risk | Strategy
Requirements Changes | List information on requirements change impact, maximize information hiding in the design.
Organizational restructuring | Prepare a brief document for senior management showing how the project is making a very important contribution to goals of the business.
Database performance | Investigate the possibility of higher-performance database.
Underestimated development | Investigate buying in components, investigate use of program generator.

## Slide 17: Risk monitoring
Assess each identified risks regularly to decide whether or not it is becoming less or more probable.
Also access whether the effects of the risk have changed.
Each key risk should be discussed at management progress meetings.

## Slide 18: Risk indicators
Risk Type | Potential indicators
Technology | Late delivery of hardware or support software, may be reported technology problems.
People | Poor staff morale, poor relationship amongst team member, job availability
Organizational | Organizational Gossip,lack of attention by senior management.
Tools | Reluctance by team members to use tools, Complaint about CASE tools, demands for higher- powered workstations
Requirements | Many requirement change request, customer complaints.
Estimation | Failure to meet agreed schedule, failure to clear reported defects.