## Slide 1: Project Management Tools

## Slide 2: Learning Objectives
Introduction of PM Tools
PMI’s Knowledge Areas
Technical Fundamentals in SPM
Lifecycle Relationships
Classic Mistakes Product-Process-Peoples-Technology Mistakes

## Slide 3: Project Management Tools
“Tool" is any self-contained concept, practice, technique, or software package that can be applied independently to a software project, in order to improve the way it is performed [1].
Risk management, for example, is as much of a tool as Microsoft Project or Subversion.
Notes: Most people think of a tool as a piece of software that can be used to manage a project schedule, track defects, or automate other tasks, in order to increase productivity on a project.
1. The idea behind these tools and techniques is to allow a project manager to pick and choose only those practices that solve the specific problems she is having with her own projects.
2. can be implemented by a single person, either working alone or in a team environment.
3.

## Slide 4: Why Use Project Management Tools and Techniques?
Focus and clarify our thinking so that we proceed in a systematic, effective, and efficient manner
Identify everything that needs to be considered and done to reach a goal (includes what is to be communicated and to whom)
Identify who will do what and time frames
Reduce the confusion, frustration, backtracking, and errors that can be associated with developing or introducing something new

## Slide 5: Project Management Tools and Techniques
Project management tools and techniques assist project managers and their teams in various aspects of project management
Some specific ones include:
  Project charter, scope statement, and WBS (scope)
  Gantt charts, network diagrams, critical path analysis, critical chain scheduling (time)
  Cost estimates and earned value management (cost)

## Slide 6: Super Tools
“Super tools” are those tools that have high use and high potential for improving project success, such as:
  Software for task scheduling (such as project management software)
  Scope statements
  Requirements analyses
  Lessons-learned reports
Tools already extensively used that have been found to improve project importance include:
  Progress reports
  Kick-off meetings
  Gantt charts
  Change requests

## Slide 7: PM Tools: Software
Low-end
  Handle single or smaller projects well, cost under $200 per user
  Basic features, tasks management, charting
  MS Excel, Milestones Simplicity
Mid-market
  Handle larger projects, multiple projects and users, analysis tools
  MS Project (approx. 50% of market)
  cost $200-600 per user, Project 2007 most popular

## Slide 8: PM Tools: Software - II
High-end
  Very large projects, specialized needs, enterprise
  AMS Real-time (Advanced Management Solution)
  Primavera Project Manager
  Often licensed on a per-user basis, like VPMi Enterprise Online

## Slide 9: Tools: Gantt Chart

## Slide 10: Tools: Network Diagram

## Slide 11: PMI’s 10 Knowledge Areas
PMI has divided the large field of project management into 10 more digestible parts, which it calls the 10 project management knowledge areas in its A Guide to the Project Management Body of Knowledge (PMBOK).
Project integration management
Scope
Time
Cost
Quality
Human resource
Communications
Risk
Procurement
Stakeholder management
Notes: If you study for the PMI certification you’ll need to know these

## Slide 12: Overview of Knowledge Areas
Identify and describe the ten knowledge areas
Identify your current development needs and strengths in the processes in each knowledge area

## Slide 13: Overview of Knowledge Areas
Cost
Time
Scope
Integration
Human Resources
Communications
Risk
Procurement
Stakeholder management
Quality

## Slide 14: Project Integration Management
“A subset of project management that includes the processes required to ensure that the various elements of the project are properly coordinated.”
Project plan development
Project plan execution
Overall change control

## Slide 15: The Integration Challenge Software Product Development Example
Proposal Request
Proposal Phase
Requirements Analysis Phase
General Design Phase
Detailed Design Phase
Code and Debug
Overlapped phases can yield cost and schedule benefits but add to the integration challenge

## Slide 16: Characteristics of Effective Integration
Overlapped processes
Effective change control and communication systems
Reduced development time and cost
Early and ongoing involvement of all stakeholders
Early visibility of results
Early problem identification and resolution
Use all relevant expertise at earliest meaningful time

## Slide 17: Project Scope Management
“Includes the processes required to ensure that the project includes all of the work required, and only the work required to complete the project successfully.”
Initiation
Scope planning
Scope definition
Scope verification
Scope change control

## Slide 18: Key Scope Concepts
Configuration Management
  A mechanism to track budget, schedule variances, and deliverable versions
Specification
  A precise definition of a physical item, procedure, service, or result for the purpose of purchase and/or implementation of an item or service
Sources of Scope Change
  Variation in government regulations
  Failure to include a required feature in the design of the product
  Customers who change their minds about the desired nature of the deliverable

## Slide 19: Key Scope Concepts (continued)
Work Breakdown Structure
A deliverable-oriented grouping of process elements that organizes and defines the total scope of the project
Each descending level represents an increasingly detailed definition of a project component
Project components may be products or services

## Slide 20: Project Time Management
Definition
  A subset of project management that includes the processes required to ensure timely completion of the project
Processes
  Activity definition
  Activity sequencing
  Activity duration estimating
  Schedule development
  Schedule control

## Slide 21: Purpose of Scheduling Processes
Illustrates interdependence of project activities, work packages, and work units
Monitors and controls timing of project work
Guides the allocation of resources
Drives personnel availability issues and activities

## Slide 22: Remodel Kitchen WBS
Purchase
Appliances
Purchase
Fixtures
Remodel Kitchen
Design
Purchase
Carpentry
Electrical
Level 1
Level 2

## Slide 23: Kitchen Remodeling Precedence Relationships

## Slide 24: Project Cost Management
“… the processes required to ensure that the project is completed within the approved budget.”
Resource planning
Cost estimating
Cost budgeting
Cost control

## Slide 25: One Performance Measurement
Earned Value
  Budgeted Cost of Work Performed (BCWP)
Related Terms
  Budgeted Cost of Work Scheduled (BCWS)
  Actual Cost of Work Performed (ACWP)
  Budget at Completion (BAC)
Notes: To illustrate the difference between the three terms, assume that a schedule contains a task "Test hardware" estimated to run from 1 January to 10 January and to cost $1000, and that this is a simple effort with no overhead or allocated costs. However on 5 January, halfway through the time allowed, the work is 30% complete and has spent $250.
BCWP is $1000 (budgeted cost) times 30% (work performed), or $300
BCWS is $1000 (budgeted cost) times 50% (scheduled amount), or $500
ACWP is $250

## Slide 26: Project Quality Management
“A subset of project management that includes the process required to ensure that the project will satisfy the needs for which it was undertaken.”
Quality planning
Quality assurance
Quality control

## Slide 27: Project HR Management
“… the processes required to make the most effective use of the people involved with the project.”
Organizational planning
Staff acquisition
Team development
Notes: team building factors such as cultural diversity, team climate, and global environment.

## Slide 28: Responsibility Chart

## Slide 29: Responsibility Chart Characteristics
Work Package Level
Components
  WBS activity
  Responsible organization
  Responsible position title or person
  Type of responsibility
    Approving authority
    Prime implementation accountability
    Support
    Notification
Notes: The work package level is the lowest level of a work breakdown structure (WBS).

## Slide 30: Project Risk Management
“… the processes concerned with identifying, analyzing, and responding to project risk.”
Risk identification
Risk quantification
Risk response development
Risk response control

## Slide 32: Project Communications Management
“… the timely and appropriate generation, collection, dissemination, storage, and ultimate disposition of project information.”
Communications planning
Information distribution
Performance reporting
Administrative closure

## Slide 33: Project Procurement Management
“… includes the processes required to acquire goods and services from outside the performing organization.”
Procurement planning
Solicitation planning
Solicitation
Source selection
Contract administration
Contract closeout

## Slide 34: Project Stakeholder Management
“…Includes the processes required to identify the people, groups, or organizations that could impact or be impacted by the project, to analyze stakeholder expectations and their impact on the project, and to develop appropriate management strategies for effectively engaging stakeholders in project decisions and execution.”
Identify Stakeholders
Plan Stakeholder Engagement
Manage Stakeholder Engagement
Monitor Stakeholder Engagement

## Slide 35: Summary
Identified and described the nine knowledge areas and the core processes in each
Allocated typical processes and activities to their appropriate knowledge area

## Slide 37: Technical Fundamentals
Requirements
Analysis
Design
Construction
Quality Assurance
Deployment

## Slide 38: Project Phases
All projects are divided into phases
All phases together are known as the Project Life Cycle
Each phase is marked by completion of Deliverables
Identify the primary software project phases

## Slide 39: Lifecycle Relationships

## Slide 40: Seven Core Project Phases

## Slide 41: Project Phases A.K.A.

## Slide 42: Phases Variation
Notes: one size SLC cannot possibly fit all.
unique projects require unique models, or combinations of models, to succeed.

## Slide 43: First Principles
One project size does not fit all
Patterns and Anti-Patterns
Spectrums
  Project types
  Sizes
  Formality and rigor (severity)
Notes: Like families, each dysfunctional in it’s own “special way”
Classic Mistakes later == Anti
Different sizes need different choices from the PM

## Slide 44: Why Rapid Development
Faster delivery
Reduced risk
Increased visibility to customer
Don’t forsake quality

## Slide 45: Strategy
Classic Mistake Avoidance
Apply Development Fundamentals
Risk Management
Apply Schedule-Oriented Practices
Notes: McConnell refers to “Pillars”
These provide balance

## Slide 46: Four Project Dimensions
People
Process
Product
Technology
Notes: Whether you're bogged down trying to avoid mistakes or cruising at top speed with highly effective schedule-oriented practices, your software project operates along four important dimensions: people, process, product, and technology.
Peopleware issues
10-to-1 difference in Dev productivity
Teams 3 or 5 to 1 diff
Process (The process leverages people's time, or it throws up one stumbling block after another)
Dev basics, Risk managment, QA, lifecycle planning, customer orientation
Product ()
Most tangible dimension
Technology (Technology assists the development effort, or it thwarts developers' best attempts)

## Slide 47: Triple Constraint
Scope
Time
Cost
Traditional Project Management Constraints
Every project has 3 constrains Scope goals: What work will be done? Time goals: How long should it take to complete? Cost goals: What should it cost?

## Slide 48
Time constraint may lead to less quality because of ?
less time for analysis,
less time for planning,
less time for reviewing,
less time for checking,
less time for monitoring,
less time for control
Traditional Project Management Constraints

## Slide 49
Cost constraint may lead to less quality because of ?
Hiring less skilled people,
Getting less quality resources
Ignoring some customer requirements
Traditional Project Management Constraints

## Slide 50
Scope limitations may lead to less quality because of ?
Scope limitations may lead to Ignore some customer requirements
shortcuts
Traditional Project Management Constraints

## Slide 51: Quadruple Constraint
Scope
Time
Cost
Quality
Traditional Project Management Constraints
Quality is a key factor for projects success We may add Quality as a 4th constraint: The Quadruple constraint =The Triple constraint +Quality constraint

## Slide 52: Trade-off Triangle
Fast, cheap, good. Choose two.

## Slide 53: Trade-off Triangle
Know which of these are fixed & variable for every project

## Slide 54: People
“It’s always a people problem” Gerald Weinberg, “The Secrets of Consulting”
Developer productivity: 10-to-1 range
Improvements:
  Team selection
  Team organization
  Motivation
Notes: Teams: 5-to-1 range

## Slide 55: People 2
Other success factors
  Matching people to tasks
  Career development
  Balance: individual and team
  Clear communication

## Slide 56: Process
Is process stifling?
2 Types: Management & Technical
Development fundamentals
Quality assurance
Risk management
Lifecycle planning
Notes: Stifling - making one feel constrained or oppressed
cut time-to-market
Improve quality

## Slide 57: Product
The “tangible” dimension
Product size management
Product characteristics and requirements
Feature creep management

## Slide 58: Technology
Often the least important dimension
Language and tool selection
Value and cost of reuse

## Slide 59: Classic Mistakes
Types
  People-Related
  Process-Related
  Product-Related
  Technology-Related
Notes: Seductive: good reason for decisions at the time
Some are IT, most not
We’ll visit these throughout course
Gilligan’s Island: new scheme, get off island, seems to work, then fails
Being aware can help prevent
Class discussion

## Slide 60: People-Related Mistakes Part 1
Undermined motivation
Weak personnel
  Weak vs. Junior
Uncontrolled problem employees
Heroics
Adding people to a late project
Notes: Motivation: studies show has largest impact
Don’t undermine Morale
    --from giving a hokey pep talk at the beginning to requiring overtime in the middle and going on a long vacation while the team worked through the holidays to providing bonuses that work out to less than a dollar per overtime hour at the end.
    2nd greatest influence on productivity
  Junior != bad
Uncontrolled: most common developer complain about their managers
  the team knew that Chip was a bad apple, but the team lead didn't do anything about it. The result--redoing all of Chip's work--was predictable.
Heroics. Company hostage.
“Can-do”, “how high” attitudes
  A small development team held an entire company hostage because they wouldn't admit that they were having trouble meeting their schedule. An emphasis on heroics encourages extreme risk taking and discourages cooperation among the many stakeholders in the software-development process.
Brooks, reading assignment
  adding people to a late project to pouring gasoline on a fire

## Slide 61: People-Related Mistakes Part 2
Noisy, crowded offices
Customer-Developer friction
Unrealistic expectations
Politics over substance
Wishful thinking
Notes: 60%of developers feel unsatisfactory environment: need quite and privacy
  Workers who occupy quiet, private offices tend to perform significantly better than workers who occupy noisy, crowded work bays or cubicles. Noisy, crowded work environments lengthen development schedules.
MS offices
Friction: classic differing viewpoints
  The primary effect of this friction is poor communication, and the secondary effects of poor communication include poorly understood requirements, poor user-interface design, and, in the worst case, customers' refusing to accept the completed product. On average, friction between customers and software developers is so severe that both parties consider canceling the project (Jones 1994). Such friction is time-consuming to overcome, and it distracts both customers and developers from the real work of the project.
Results in ‘poor communication’
  Passive-aggressive
Realistic Expectations: 1 of top 5 reasons for success of in-house projects
  Perception woe
  Sometimes they promise a pie-in-the-sky feature set.
Politics
  Managing-up
  "Politicians" specialized in "managing up," concentrating on relationships with their managers. "Researchers" concentrated on scouting out and gathering information. "Isolationists" kept to themselves, creating project boundaries that they kept closed to non-team members. "Generalists" did a little bit of everything.
  Putting politics over results is fatal to speed-oriented development.
Wishful
  Wishful thinking isn't just optimism. It's closing your eyes and hoping something works when you have no reasonable basis for thinking it will. Wishful thinking at the beginning of a project leads to big blowups at the end of a project. It undermines meaningful planning and may be at the root of more software problems than all other causes combined.
  Cognitive dissonance
  Closing your eyes and hoping
  McConnell: maybe causes the most problems in software development

## Slide 62: People-Related Mistakes Part 3
Lack of effective project sponsorship
Lack of stakeholder buy-in
Lack of user input
Notes: Sponsor: a must, no power
All players must buy-in
  That includes the executive sponsor, team leader, team members, marketing, end-users, customers, and anyone else who has a stake in it.
User input: Survey: number 1 reason for success
W/O input: guessing

## Slide 63: Process-Related Mistakes Part 1
Optimistic schedules
Insufficient risk management
Contractor failure
Insufficient planning
Abandonment of plan under pressure
Notes: Similar to wishful thinking
Puts unnecessary pressure
Risk Mgmt:
  Risks will manage you
  if you don't actively manage risks, only one thing has to go wrong to change your project from a rapid-development project to a slow-development one.
Contractor: late, poor quality, or fails to meet specifications
Requires lots of management
Insufficient planning: “if you don’t care where you’re going, any plan will do”
Abandonment
  Out the window
  Fall into code-and-fix mode
  The result was that work after that point was uncoordinated and awkward--to the point that Jill even started working on a project for her old group part of the time and no one even knew it.

## Slide 64: Process-Related Mistakes Part 2
Wasted time during fuzzy front end
Shortchanged upstream activities
Inadequate design
Shortchanged quality assurance
Notes: fuzzy: before sign-off
  spend months or years in the fuzzy front end and then to come out of the gates with an aggressive schedule.
Upstream:
  Lack of analysis and design
  10 to 100 times more costly
  5 hrs vs. 50
  since requirements analysis, architecture, and design don't directly produce code, they are easy targets.
  "jumping into coding," the results of this mistake are all too predictable.
Design:
  Seen schedules w/o it at all
  by creating a pressure-cooker environment that makes thoughtful consideration of design alternatives difficult.
  The design emphasis is on expediency rather than quality
QA:
  Before you can keep a project on track, you have to be able to tell whether it's on track.
  Seems easy to compress
  1 day QA == 3 to 10 later

## Slide 65: Process-Related Mistakes Part 3
Insufficient management controls
Frequent convergence
Omitting necessary tasks from estimates
Planning to catch-up later
Code-like-hell programming
Notes: Management controls
  Need to be able to track
  We’ll cover lots of these
  PMI
Convergence
  On rush projects, there is a tendency to force convergence early.
  Waste of time
Missing tasks
  Often 20-30% of a schedule
Catch-up later
  If you're working on a six-month project, and it takes you three months to meet your two-month milestone, what do you do?
  How many times have you seen a project catch-up?
  Only by all-nighters
Like hell
  “Entrepreneurial” approach
  think that fast, loose, all-as-you-go coding is a route to rapid development.

## Slide 66: Product-Related Mistakes
Requirements gold-plating
  Gilding the lily
Feature creep
Developer gold-plating
  Beware the pet project
Push-me, pull-me negotiation
Research-oriented development
Notes: Gold
  Gilding the lily
  Some projects have more requirements than they need right from the beginning.
  Performance is required more often than need be, and that can unnecessarily lengthen a software schedule.
Feature creep
  25% average change in req.
Dev. Gold
  Nifty new technology
  Developers are fascinated by new technology and are sometimes anxious to try out new features of their language or environment
  Pet project
Push-me
  Slip schedule + add features
  One bizarre negotiating ploy occurs when a manager approves a schedule slip on a project that's progressing slower than expected and then adds completely new tasks after the schedule change.
Research vs. Development

## Slide 67: Technology-Related Mistakes
Silver-bullet syndrome
Overestimated savings from new tools and methods
Switching tools in mid-project
Lack of automated source-code control
Notes: who’s heard of ‘silver bullet’ (not the beer)
SCM
  Jones: 10% month, I see more

## Slide 68: References
[1] – Applied Software Project Management By: Jennifer Greene, Andrew Stellman (O'Reilly)
[2] - “Rapid Development”, McConnell (Chapter-3)