## Slide 1: Chapter 7: Project Cost Management
Information Technology Project Management, Seventh Edition
Note: See the text itself for full citations.

## Slide 2: Learning Objectives
Understand the importance of project cost management
Explain basic project cost management principles, concepts, and terms
Describe the process of planning cost management
Discuss different types of cost estimates and methods for preparing them

## Slide 3: Learning Objectives
Understand the processes of determining a budget and preparing a cost estimate for an information technology (IT) project
Understand the benefits of earned value management and project portfolio management to assist in cost control
Describe how project management software can assist in project cost management

## Slide 4: The Importance of Project Cost Management
IT projects have a poor track record for meeting budget goals
The CHAOS studies found the average cost overrun (the additional percentage or dollar amount by which actual costs exceed estimates) ranged from 180 percent in 1994 to 43 percent in 2010
A 2011 Harvard Business Review study reported an average cost overrun of 27 percent. The most important finding was the discovery of a large number of gigantic overages or “black swans”

## Slide 5: What Went Wrong?
The U.S. government, especially the IRS, continues to provide examples of how not to manage costs
  A series of project failures by the IRS in the 1990s cost taxpayers more than $50 billion a year
  In 2006, the IRS was in the news for a botched upgrade to its fraud-detection software, costing $318 million in fraudulent refunds that didn’t get caught
  A 2008 Government Accountability Office (GAO) report stated that more than 400 U.S. government agency IT projects, worth an estimated $25 billion, suffer from poor planning and underperformance
The United Kingdom’s National Health Service IT modernization program was called the greatest IT disaster in history with an estimated $26 billion overrun. It was finally scrapped in 2011.

## Slide 6: What is Cost and Project Cost Management?
Cost is a resource sacrificed or foregone to achieve a specific objective or something given up in exchange
Costs are usually measured in monetary units like dollars
Project cost management includes the processes required to ensure that the project is completed within an approved budget

## Slide 7: Project Cost Management Processes
Planning cost management :determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost.
Estimating costs: developing an approximation or estimate of the costs of the resources needed to complete a project
Determining the budget: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
Controlling costs: controlling changes to the project budget
Notes: Cost Baseline: Cost Baseline is the authorized time-phased spending plan for the project on which the project cost performance is to be measured against.

## Slide 8: Figure 7-1. Project Cost Management Summary

## Slide 9: Basic Principles of Cost Management
Most members of an executive board better understand and are more interested in financial terms than IT terms , so IT project managers must speak their language
  Profits are revenues minus expenditures
  Profit margin is the ratio of revenues to profits
  Life cycle costing considers the total cost of ownership, or development plus support costs, for a project
  Cash flow analysis determines the estimated annual costs and benefits for a project and the resulting annual cash flow

## Slide 10: Table 7-1. Cost of Downtime for IT Applications
Source: The Standish Group International, “Trends in IT Value,” www.standishgroup.com (2008).

## Slide 11: What Went Right?
Many organizations use IT to reduce operational costs
Technology has decreased the costs associated with processing an ATM transaction:
  In 1968, the average cost was $5.
  In 1978, the cost went down to $1.50
  In 1988, the cost was just a nickel.
  In 1998, it only cost a penny.
  In 2008, the cost was just half a penny!
Investing in green IT and other initiatives has helped both the environment and companies’ bottom lines. Michael Dell, CEO of Dell, reached his goal to make his company “carbon neutral” in 2008. As of March 2012, Dell had helped its customers save almost $7 billion in energy costs

## Slide 12: Types of Costs and Benefits
Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars. For Example,
  Paying employee wages,
  Computer systems,
  Assets such as equipment, land, or a ne factory
Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms. Intangible costs can include:
  A fall in employee morale
  Damage to a company's reputation or brand
  Customer satisfaction
  Loss of intellectual capital following employee layoffs

## Slide 13: Types of Costs and Benefits
Direct costs are costs that can be directly related to producing the products and services of the project
Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project
Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs
Notes: Indirect costs cost of electricity, paper towels, and other necessities

## Slide 14: More Basic Principles of Cost Management
Learning curve theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced
Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
  Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
  Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns

## Slide 15: Planning Cost Management
The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
A cost management plan includes:
  Level of accuracy and units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions
Notes: Level of accuracy: amount of contingency funds to include, such as 10 or 20 percent. Units of measure: such as labor hours or days, should be defined.
Organizational procedures links: (WBS) component used for project cost accounting as the control account (CA). Each control account is often assigned a unique code that is used in the organization’s accounting system.
Control thresholds: a specified amount of variation allowed before action needs to be taken, such as ±10 percent of the baseline cost.
Rules of performance measurement: earned value management (EVM) how often

## Slide 16: Estimating Costs
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
It’s important to know the types of cost estimates, how to prepare cost estimates, and typical problems associated with IT cost estimates

## Slide 17: Table 7-2. Types of Cost Estimates
Notes: Many organizations develop budgets at least two years into the future.

## Slide 18: More on Cost Estimates
The number and type of cost estimates vary by application area. The Association for the Advancement of Cost Engineering International identifies five types of cost estimates for construction projects: order of magnitude, conceptual, preliminary, definitive, and control
Estimates are usually done at various stages of a project and should become more accurate as time progresses
A large percentage of total project costs are often labor costs
Notes: order of magnitude: based on experience and judgment, historical values and charts, rules of thumb, and simple mathematical calculations. E.g. Square Foot Costs
Conceptual: establishing a cost per usable unit from past projects and multiplying this cost times the number of units being proposed. E.g. Cost per student
Preliminary: the Study or Feasibility Estimate
Control: Control or bid/tender estimate, Estimate methodology is the detailed unit cost with bulk material
Definitive: Used after the costs, not just quantities of materials, are known. For example, after the project is tendered (or quotes have been received), rather than just designed.

## Slide 19: Table 7-3. Maximum FTE by Department by Year
Notes: full-time equivalent (FTE) staff Northwest Airlines reservation system

## Slide 20: Cost Estimation Tools and Techniques
Basic tools and techniques for cost estimates:
  Analogous or top-down estimates: use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
  Bottom-up estimates: involve estimating individual work items or activities and summing them to get a project total
  Parametric modeling uses project characteristics (parameters) in a mathematical model to estimate project costs
Notes: $50 per line of code for a software development project

## Slide 21: Typical Problems with IT Cost Estimates
Estimates are done too quickly
People lack estimating experience
Human beings are biased toward underestimation
Management desires accuracy

## Slide 22: Sample Cost Estimate
See pages 284-289 for a detailed example of creating a cost estimate for the Surveyor Pro project described in the opening case
Before creating an estimate, know what it will be used for, gather as much information as possible, and clarify the ground rules and assumptions for the estimate
If possible, estimate costs by major WBS categories
Create a cost model to make it easy to make changes to and document the estimate

## Slide 23: Figure 7-2. Surveyor Pro Project Cost Estimate

## Slide 24: Figure 7-3. Surveyor Pro Software Development Estimate

## Slide 25: Determining the Budget
Cost budgeting involves allocating the project cost estimate to individual work items over time
The WBS is a required input to the cost budgeting process since it defines the work items
Important goal is to produce a cost baseline
  a time-phased budget that project managers use to measure and monitor cost performance

## Slide 26: Figure 7-4. Surveyor Pro Project Cost Baseline
Notes: Appropriate percentages of the total cost based on similar past projects.
- a range estimate for each item instead of one discrete amount.

## Slide 27: Controlling Costs
Project cost control includes
  Monitoring cost performance
  Ensuring that only appropriate project changes are included in a revised cost baseline
  Informing project stakeholders of authorized changes to the project that will affect costs
Many organizations around the globe have problems with cost control

## Slide 28: Earned Value Management (EVM)
EVM is a project performance measurement technique that integrates scope, time, and cost data
Given a baseline (original plan plus approved changes), you can determine how well the project is meeting its goals
You must enter actual information periodically to use EVM
More and more organizations around the world are using EVM to help control project costs
Notes: Actual information - includes whether or not a WBS item was completed, approximately how much of the work was completed, when the work actually started and ended, and how much the completed work actually cost.

## Slide 29: Earned Value Management Terms
The planned value (PV), formerly called the budgeted cost of work scheduled (BCWS), also called the budget, is that portion of the approved total cost estimate planned to be spent on an activity during a given period
Actual cost (AC), formerly called actual cost of work performed (ACWP), is the total of direct and indirect costs incurred in accomplishing work on an activity during a given period
The earned value (EV), formerly called the budgeted cost of work performed (BCWP), is an estimate of the value of the physical work actually completed
EV is based on the original planned costs for the project or activity and the rate at which the team is completing work on the project or activity to date
Notes: Planned value (PV) - activity of purchasing and installing a new web server would take one week and cost a total of $10,000 for the labor hours, hardware, and software. Actual cost (AC) – suppose that it actually took two weeks and cost $20,000, Assume that $15,000 of these actual costs were incurred during Week 1 and $5,000 was incurred during Week 2.

## Slide 30: Rate of Performance
Rate of performance (RP) is the ratio of actual work completed to the percentage of work planned to have been completed at any given time during the life of the project or activity
Brenda Taylor, Senior Project Manager in South Africa, suggests this term and approach for estimating earned value
For example, suppose the server installation was halfway completed by the end of week 1. The rate of performance would be 50% because by the end of week 1, the planned schedule reflects that the task should be 100 percent complete and only 50 percent of that work has been completed

## Slide 31: Table 7-4. Earned Value Calculations for One Activity After Week One

## Slide 32: Table 7-5. Earned Value Formulas
Notes: budget at completion (BAC)

## Slide 33: Rules of Thumb for Earned Value Numbers
Negative numbers for cost and schedule variance indicate problems in those areas
CPI and SPI less than 100% indicate problems
Problems mean the project is costing more than planned (over budget) or taking longer than planned (behind schedule)
The CPI can be used to calculate the estimate at completion (EAC)—an estimate of what it will cost to complete the project based on performance to date. The budget at completion (BAC) is the original total budget for the project

## Slide 34: Figure 7-5. Earned Value Chart for Project after Five Months

## Slide 35: Earned Value Calculations for a One-Year Project After Five Months

## Slide 36: Global Issues
EVM is used worldwide, and it is particularly popular in the Middle East, South Asia, Canada, and Europe
Most countries require EVM for large defense or government projects, as shown in Figure 7-6
EVM is also used in such private-industry sectors as IT, construction, energy, and manufacturing.
However, most private companies have not yet applied EVM to their projects because management does not require it, feeling it is too complex and not cost effective

## Slide 37: Figure 7-6. Earned Value Usage

## Slide 38: Project Portfolio Management
Many organizations collect and control an entire suite of projects or investments as one set of interrelated activities in a portfolio
Five levels for project portfolio management
  Put all your projects in one database
  Prioritize the projects in your database
  Divide your projects into two or three budgets based on type of investment
  Automate the repository
  Apply modern portfolio theory, including risk-return tools that map project risk on a curve

## Slide 39: Benefits of Portfolio Management
Schlumberger saved $3 million in one year by organizing 120 information technology projects into a portfolio
ROI of implementing portfolio management software by IT departments:
  Savings of 6.5 percent of the average annual IT budget by the end of year one
  Improved annual average project timeliness by 45.2 percent
  Reduced IT management time spent on project status reporting by 43 percent and IT labor capitalization reporting by 55 percent
  Decreased the time to achieve financial sign-off for new IT projects by 20.4 percent, or 8.4 days

## Slide 40: Best Practice
A global survey released by Borland Software in 2006 suggests that many organizations are still at a low-level of maturity in terms of how they define project goals, allocate resources, and measure overall success of their information technology portfolios. Some of the findings include the following:
  Only 22 percent of survey respondents reported that their organization either effectively or very effectively uses a project plan for managing projects
  Only 17 percent have either rigorous or very rigorous processes for project plans, which include developing a baseline and estimating schedule, cost, and business impact of projects
  Only 20 percent agreed their organizations monitor portfolio progress and coordinate across inter-dependent projects

## Slide 41: Using Software to Assist in Cost Management
Spreadsheets are a common tool for resource planning, cost estimating, cost budgeting, and cost control
Many companies use more sophisticated and centralized financial applications software for cost information
Project management software has many cost-related features, especially enterprise PM software
Portfolio management software can help reduce costs

## Slide 42: Chapter Summary
Project cost management is a traditionally weak area of IT projects, and project managers must work to improve their ability to deliver projects within approved budgets
Main processes include
  Plan cost management
  Estimate costs
  Determine the budget
  Control costs