## Slide 1
Programme Planning, Monitoring and Evaluation in Agricultural Extension

## Slide 2
PRINCIPLES OF PROGRAM PLANNING

## Slide 3
1:- Extension program should be based on past experience, present situation and future needs:
Adequate information about the people and their situation have to be collected.
Present situation is to be analyzed.
Interpreted on the basis of past experiences.
Help in arriving at the future needs.

## Slide 4
2:- Extension program should have clear objectives based on needs of the people:
Ultimate objective is to satisfy the needs of the people.
Significant objectives pertaining to important needs of the people.
What is attainable rather than what is ideal.

## Slide 5
3:- Extension program should be based on priority considering available human and natural resources:
Rural people have multitude of problems.
All problems can not be taken up at a time for solution because of
Limitation :
Trained personnel
Availability of funds.
Facilities and other resources.
Time.

## Slide 6
Wherefrom the funds, facilities, supplies and needed personnel shall be available.
How these shall be Utilized.
Programme practical and workable.
4:- Extension program should clearly define available resources and their utilization:

## Slide 7
 5:- Extension programme should have a some rules and procedures at different level

Extension programme prepared at levels should conform to each other.
Extension programme of a particular department should not be in conflict or
contradiction with the extension programme of other department.

## Slide 8
Local people should be involved:
Programme formulation to
Programme implementation level.
6:- Extension Program should ensure participation of local people

## Slide 9
Extension programmes implemented in isolation
Requires the support of many institutions and organizations to be involved.
How they shall contribute in attaining the programme.
 7:- Extension program should involve related departments, institutions, and organizations

## Slide 10
8:- Extension program should have well managed plan of work
Plan of work may be separately drawn up or incorporated in the programme.
How it will be executed.
Unless the plan of work is drawn up, the
programme remains a theoretical exercise.

## Slide 11
Not a static outline of activities.
Periodical monitoring and evaluation of results to judge its progress.
On the basis of findings of evaluation, programme should be suitably modified to facilitate its reaching the objectives.
9:- Extension program should use evaluation procedures to analyse results & to use for reconsideration

## Slide 12
Resource rich persons benefits more in comparison to resource poor.
Adequate emphasis on weaker section of the society.

10:- Extension program should ensure equal benefits among community memebers

## Slide 13
PROGRAM PLANNING PROCESS

## Slide 14
Collection of facts
Analysis of situation
Identification of problems
Determination of objectives and goals
Development plan of work and calendar of operations
Follow through plan of work and calendar of operations.
Evaluation of progress.
Reconsideration and revision of the programme

## Slide 15
Starting point of programme planning.
Pertinent data may be collected from the
available records.
Information: enterprise, levels of technology, facilities and constraints, values etc.
Collected from panchayats, cooperatives and other organizations in the areas.

## Slide 16
Data and information collected are then
analyzed with the local people.
Understanding the situation in a proper way.

## Slide 17
A proper analysis and interpretation of data shall help in correctly identifying the problems.
Only urgent and significant ones which may be solved with the available resources and with in the limits of time, should be selected.
Properly managed.

## Slide 18
Objectives are then set forth on the basis of significant need identified.
Direct and clear.
To make the objectives realistic and actionable:
Go through the data and information analyzed.
To find what could actually be done in existing situation, with the available resources and time
Which will be compatible.

## Slide 19
Plan of work should be in written form and shall indicate who shall do what job, what the change agent system, client system shall do, which institution, organizations, service department shall be involved.
Plan should have essential details and no important point should be left out.
Calendar of operations shall be prepared on the basis of plan of work.

## Slide 20
Not a routine type of work.
Training of participants, communication of information, conducting method demonstration, making regular visits and monitoring are some important functions.
Solving unforeseen problems and taking corrective steps where needed.

## Slide 21
Evaluation is the process of determining the extent to which we have been able to attain our objectives.
Evaluation has number of advantages:
Help to establish a bench mark-the situation at the start of the programme.
Shows how far our plans have progressed.
Whether we are proceeding in the right direction.
Indicate the effectiveness of a programme.
Help to locate strong and weak points in any programme or plan.

## Slide 22
On the basis of results of evaluation, the programme should be reconsidered and revised if needed.
This reconsideration should be done not only with the participants but also with the scientists, extension managers etc.
The purpose of such an exercise is to make the extension programme more effective removing the defects.

## Slide 23
MONITORING AND EVALUATION OF EXTENSION PROGRAM

## Slide 24
Evaluation as applied to the field of extension education defined as a process of systematic appraisal by which we determine the value, worth or meaning of an activity or an enterprise.
Evaluation is a process by which the values of an enterprise are ascertained or analyzed by which one is able to understand and appreciate the relative merits or deficiencies of persons, groups, programmes, situations, method and processes.

## Slide 25
 Supervising activities in progress to ensure they are on-course and on-schedule in meeting the objectives and performance targets.

## Slide 26
Monitoring and evaluation (M&E) is a process that helps improve performance and achieve results.
Its goal is to improve current and future management of outputs, outcomes and impact.
It is mainly used to assess the performance of projects, institutions and programmes set up by governments, international organizations and NGOs.
It establishes links between the past, present and future actions.

## Slide 27
Self Evaluation:
This is to be carried out every extension worker.
This require self critical attitude which is essential for extension worker.
Chances of extension worker growing and continuously improving his professional competency become greater.

## Slide 28
Internal Evaluation:
 Evaluation responsible
carried for
to by the the planning
agency
and
implementation of the programme.
Other methods are: Systematic use of diaries, reports of workers, planned visit of staff member, use of special questionnaire.
External Evaluation: Evaluation conducted by a person or a committee outside the area of operation.

## Slide 29
ensures that a program or
 Formative evaluation:
program activity is
feasible, appropriate, and
acceptable before it is fully implemented. It is usually conducted when a new program or activity is being developed or when an existing one is being adapted or modified.
Process/implementation evaluation: determines whether program activities have been implemented as intended.
Outcome evaluation: measures program effects in the target population by assessing the progress in the outcomes or outcome objectives that the program is to achieve.
Impact evaluation: assesses program effectiveness in achieving its ultimate goals.