## Slide 1: Methods of estimating activity duration
Analogy
Historical data
Expert judgment/ Expert Advise
Delphi technique
Three-point technique

## Slide 2: Analogy
Some of the activities in your WBS may be similar to activities completed in other projects. Your or others’ recollections of those activities and their durations can be used to estimate the present task’s duration. In some cases, this process may require extrapolating from the other task to this one.
In most cases, using the estimates from those activities provides estimates that are good enough.

## Slide 3: Historical Data
Every good project management methodology includes a project notebook that records the estimated and actual task durations. This historical record can be used on other projects. The recorded data becomes your knowledge base for estimating task duration. This technique differs from the previous technique in that it uses a record, rather than depending on memory. To estimate the duration of a task, you extract similar tasks from the database and compute an average. That is a simple application of the database.

## Slide 4: Seeking Expert Advice
When the project involves a breakthrough technology or a technology that is being used for the first time in the organization, there may not be any organizational experience with that technology within the organization. In these cases, you will have to appeal to outside authorities. Vendors may be a good source, as are non-competitors who use that technology.

## Slide 5: Applying the Delphi Technique 150
The Delphi technique can produce good estimates in the absence of expert advice. This is a group technique that extracts and summarizes the knowledge of the group to arrive at an estimate.
After the group is briefed on the project and the nature of the task, each individual in the group is asked to make his or her best guess of the task duration.

## Slide 6: Three-Point Technique
To use the three-point technique, you need the following three estimates of task duration:
Optimistic— The optimistic time is defined as the shortest duration one has experienced or might expect to experience given that everything happens as expected.
Pessimistic — The pessimistic time is that duration that one would experience (or has experienced) if everything that could go wrong did go wrong, yet the task was completed.
Most likely— The most likely time is that time that they usually experience.
For this method, you are calling on the collective memory of professionals who have worked on similar activities but for which there is no recorded history.

## Slide 7
    O + 4M + P
  E= ---------------
    6

## Slide 8: Cost Estimation
After you have estimated task duration and resource requirements, you have the data you need to establish the cost of the project.
When doing an estimate, you need to consider a few concepts. No matter how well you estimate cost, it is always an estimate. One of the reasons that so many projects come in over budget is that people actually believe that they have done perfect estimating and that their baseline estimate is set in stone. Remember that it is still and always will be an estimate. Anytime you are forecasting the future, as you are when you plan a project, you are dealing with some amount of uncertainty. Projects are so often over budget because the budget itself is an estimate, not an exact mathematical calculation. Even experienced cost estimators miss the mark.

## Slide 9: Estimation Methodologies
Bottom Up
Top down
Analogy
Expert Judgment
Parametric or Algorithmic Method
  Using formulas and equations
  Lines of Code (LOC)
  Function points
  CoCoMo

## Slide 10: Code-based Estimates
LOC Advantages
  Commonly understood metric
  Actuals easily measured
LOC Disadvantages
  Difficult to estimate early in cycle
  Counts vary by language
  Many costs not considered (ex: requirements)
  Code generators produce excess code

## Slide 11: LOC Estimate Issues
How do you know how many in advance?
What about different languages?
What about programmer style?
Stat: avg. programmer productivity: 3,000 LOC/yr
Most algorithmic approaches are more effective after requirements (or have to be after)

## Slide 12: Function Points
Software size measured by number & complexity of functions it performs
More methodical than LOC counts
It is designed to estimate and measure the time, and thereby the cost, of developing new software applications and maintaining existing software applications.
It is also useful in comparing and highlighting opportunities for productivity improvements in software development.
It was developed by A.J. Albrecht of the IBM Corporation in the early 1980s.

## Slide 13: Important FPA notes
Measured from the user's perspective
Technology-independent
Low cost
Repeatable
Work well with use cases

## Slide 14: Functional Units of FP
External Input (EI): An EI is the information that comes from outside to the system for the processing.
External Output (EO): An EO is the processed information to the outside world.
External Query (EQ): An EQ is the processed information to the outside world according to the information required by the user.

## Slide 15
Internal Logical Files (ILF): A user identifiable group of logically related data maintained with the system.
External Logical Files (ELF): A user identifiable group of logically related data referenced by the system, but maintained within another system.

## Slide 16: Functional Units of FP