## Slide 1: Software Project Management
Lecture 2
Software Project Planning
BSIT 6th
University of Sargodha
Notes: According to the Standish Group in 1995, only 16% of software projects were successful, 53% challenged (that is cost overruns, budget overruns or content deficiencies) and 31% cancelled

## Slide 2: Overview
Step Wise project planning framework (next 3 slides)
Preparation of a software project plan
Activity Planning and scheduling the activities in software project management
Various approaches towards activity plan
Various scheduling techniques such as sequencing and CPM

## Slide 3: Step Wise – An Overview
0
Select
project
1 Identify
project scope
and objectives
2 Identify
project
infrastructure
3
Analyse project
characteristics
to next slide

## Slide 4: Step Wise – An Overview (cont’d)
4
Identify the
products and activities
5
Estimate efforts
for activity
6
identify
activity risks
For each activity
from previous slide
to next slide
Review
Lower level detail
from next slide

## Slide 5: Step Wise – An Overview (cont’d)
7
Allocate
resources
8
Review/
publicize plan
9
Execute
plan
10
Lower level
planning
to previous slides
from previous slide

## Slide 6: Step Wise – An Overview (cont’d)
Step 0: Select project
Step 1: Identify project scope and objectives
Step 2: Identify project infrastructure
Step 3: Analyze project characteristics
Step 4: Identify project products and activities
Notes: Step 0: Aim is to decide whether a project is worth undertaking.
A project is initiated somehow. This is not a planning activity.
It may need to decide whether the project is worth undertaking
It may need to evaluate the project. Project evaluation has been studied in Lecture 3.

## Slide 7: Step Wise - An Overview (cont’d)
Step 5: Estimate effort for each activity
Step 6: Identify activity risks
Step 7: Allocate resources
Step 8: Review/publicize plan
Step 9: Execute plan
Step 10: Execute lower levels of planning
Notes: Both steps 9 and 10 need detailed planning of each activity as the project is executed.

## Slide 8: Step 1: Identify Project Scope and Objectives
Step 1.1 Identify objectives and practical measures of the effectiveness in meeting those objectives
Step 1.2 Establish a project authority
  To ensure the unity of purpose among all persons concerned
Notes: Step 1: Aim is to have a well defined project scope and objectives.
Managers need to ensure that all members are clear about the project and its objectives; and are committed to the success of the project.

## Slide 9: Step 1: Identify Project Scope Objectives (cont’d)
Step 1.3 Identify all stakeholders in the project and their interests
Step 1.4 Modify objectives in the light of stakeholder analysis
Step 1.5 Establish methods of communication between all parties

## Slide 10: Step 2: Identify Project Infrastructure
Step 2.1 Identify relationship between the project and strategic planning
  To prioritize project components
  To establish a framework within which the system fits
  To ensure the hardware and software standards are followed
Notes: Step 2: Aim is to know the precise nature of the project infrastructure

## Slide 11: Step 2: Identify Project Infrastructure (cont’d)
Step 2.2 Identify installation standards and procedures
  more appropriate name: “Identify standards and procedures related to the software project”
Step 2.3 Identify project team organization
Notes: Gantt chart — A standard format for displaying project schedule information by listing project activities and their corresponding start and finish dates in calendar form
Step 2.2 Elaborate the following standards
1. software development procedures and standards
2. quality procedures and standards
3. change control and configuration management standards
4. project planning and control standards
Step 2.3 It is quite often that the organisation has some control over the "overall structure" of the project team.
However, if project manager does have some control, this would be considered at a later stage in resource allocation, which will be discussed in Lecture 8.

## Slide 12: Step 3: Analyse Project Characteristics
Step 3.1 Distinguish the project as either objective-driven or product-driven
Step 3.2 Analyse other project characteristics (including quality-based ones)
Step 3.3 Identify high level project risks
Step 3.4 Take into account user requirements concerning implementation
Notes: Step 3: Aim is to ensure the use of appropriate methods for the project
Step 3.1 As system development advances, it tends to become more product-driven, although the underlying objectives always remain and must be respected.
Step 3.3 Consider those risks that affect the successful outcome of the project
Where? Possibly the following:
the operational or development environment,
the technical nature of the project
the type of product being developed
Step 3.4 Sometimes, the client's organisation may have their own stadnards and procedures.
An example may be that departments in government may require the use of SSADM (Structured System Analysis and Design Methodology).
Another example may be that DoD (Department of Defense) has their own standards and procedures.

## Slide 13: Step 3: Analyse Project Characteristics (cont’d)
Step 3.5 Select general lifecycle approach in the light of the above
Step 3.6 Review overall resource estimates
  Up to this stage,
  the major risks of the project are identified
  the overall approach of the project is decided
  So, it is a good place to re-estimate the required effort and other resources for the project
Notes: Step 3.5
If user requirements are unclear, a prototyping approach might be used.
Step 3.6
A benefit is to give you a better understanding on the current situation.

## Slide 14: Step 4: Identify Project Products and Activities
Step 4.1 Identify and describe project products
  Identify all the products related to the project
  Account for the required activities
Step 4.2 Document generic product flows
  See book Product Flow Diagram (flow of modules)
Step 4.3 Recognize product instances
Notes: Step 4: Aim is to have a more detailed planning of the individual activities that will be needed
Step 4.1
Project products include nature of project, purpose, scope, end users etc

## Slide 15: Step 4: Identify Project Products and Activities(cont’d)
Step 4.4 Produce an ideal activity network
  Activity network shows the tasks that have to be carried out as well as their sequence of execution for the creation of a product from another
  Draw activity network diagram (flow of activities)
Step 4.5 Modify the ideal to take into account need for stages and checkpoints
  To check compatibility of products of previous activities
  Draw sequence diagram
Notes: See activity network diagram from Google, no diagram in text book-1
4.5: aim is to make sequence of activities

## Slide 16: Step 5: Estimate Effort for Each Activity
Step 5.1 Carry out bottom-up estimates
  need to estimate staff effort, time for each activity, and other resources
Step 5.2 Revise plan to create controllable activities
  need to break a task into a series of manageable sub-tasks
Notes: Step 5.1
  Different estimation methods may be used depending on the type of activity.
  Calculate the overall duration of project based on the estimated time for each activity in the activity network.
Step 5.2
If an activity involving system testing requires 12 weeks, it is better to break the activity into a series of sub-tasks.

## Slide 17: Step 6: Identify Activity Risks
Step 6.1 Identify and quantify the risks of each activity
Step 6.2 Plan risk reduction and contingency measures where appropriate
Step 6.3 Adjust overall plans and estimates to take account of risks

## Slide 18: Step 7: Allocate Resources (Staffing)
Step 7.1 Identify and allocate resources
  type of staff needed for each activity
  staff availabilities are identified
  staff are provisionally allocated to task
Step 7.2 Revise plans and estimates to take into account resource constraints
  staffing constraints
  staffing issues
Notes: Step 7.1 Staff expertise should be considered.

## Slide 19: 8: Identify Project Scope and Objectives