## Slide 1: Programme Planning

## Slide 2: Programme
Programme is the total educational job being done in particular setting.
Planning
“It is a process which involves studying the past and present in order to forecast the future” and in the light of that forecast determining the goal to be achieved

## Slide 3
Programme Planning
It is a Decision making process involving critical analysis of the existing situation and the problems, evaluation of the various alternatives to solve these problems and the selection of the relevant ones, giving necessary priorities based upon local needs and resources

## Slide 4: Principles of Extension Programme Planning
Extension programme should be based on an analysis of the past experiences, present situation and future needs
Extension programme should have clear and significant objectives, which could satisfy important needs of the people
Extension programme should fix up priority on the basis of available resources and time

## Slide 5
Extension programme should clearly indicate the availability and utilization of resources
Extension programme should have a general agreement at various levels
Extension programme should involve people at the local level
Extension programme should involve relevant institution and organizations
Extension programme should have definite plan of work
Extension programme should provide for evaluation of results and reconsideration of the programme
Extension programme should provide for equitable distribution of benefits amongst the members of the community

## Slide 6
Steps in Ext. programme Planning

## Slide 7
2
6
3
1
8
4
5
7
Collection of facts
Analysis of Situation
Identification of Problems
Determination of objectives & goals
Developing plan of work and calendar of operations
Follow through plan of work and calendar of operations
Evaluation of progress
Reconsideration and revision of the programme
Programme Determination
Programme implementation
Steps in Extension Programme Planning

## Slide 8: Evaluation
“Evaluation is the process of judging the value or worth of an individuals achievements or characteristics”
“Evaluation as the process for determining the value of anything”
Programme evaluation
…….is the determination of the extent to which the desired objectives have been attained
Evaluation is a comparison of the situation before and after

## Slide 9: Types of Evaluation
Formative Evaluation
….when programme activities are forming or in progress
Summative Evaluation
….when programme activities completed ….at the end of any programme ….focus on the “Product” rather than “process”
Meta Evaluation
….evaluation of evaluation…to determine the quality or value of evaluation

## Slide 10: Steps in programme Evaluation
Object description
Planning evaluation
Preparing the evaluation design/method
Data collection
Data analysis
Evaluation report

## Slide 11: Factors affecting adoption process
A. Characteristics of Innovation
1. Economic cost
2. Consistency with values
3. Complexity
4. Divisibility
5. Visibility

## Slide 12
B. Characteristics of Adopters
1. Age
2. Education
3. Income
4. Landholding
5. Cosmopolitan outlook
6. Use of Information sources

## Slide 13
B. Constraints of System
1. Values and norms
2. Traditional authority structure
3. Feudalism
4. Bureaucracy’ s prestigious position

## Slide 14: Domains of Learning (Bloom, 1956)
1. Cognitive domain (Knowledge)
The cognitive domain involves the development of our mental skills and the gaining knowledge
2. Psycho-motor domain (Skill)
Manual or physical skills
3. Affective domains (Attitude)
The affective domain involves our feelings, emotions and attitudes

## Slide 15: Adopter categories (Farmers)

## Slide 16: Stages Adoption Process