## Slide 1
Software Testing & Quality Engineering
Project tracking & Controls
Chapter 8
Linda Westfall Quality Press

## Slide 2: Objectives
  Project Tracking and Control
  Tracking Methods
  Project Reviews and Program Reviews

## Slide 3: Critical project performance measures include timeliness, budget variance, and resource usage. Project measurements must then be determined and a system for tracking, monitoring, and reporting progress is established. In medium to large projects, milestones (critical checkpoints) are established in the planning stage and the project monitored against these milestones. The critical path method (CPM) is discussed earlier can be built into the quality information system for projects of any size. Thorough periodic project reviews are conducted, including assessment of schedules against the critical path, expenditures against budgets, resource utilization against plans, implementation results achieved, a possible reevaluation of risks, and any major issues impacting project continuance. Based on these reviews, the project may be continued as planned, modified, put on hold, or canceled. A similar review is conducted to evaluate the results when the project is completed.

## Slide 4: The control cycle
Notes: Define objectives – at the beginning of the project we decide on what we want to achieve
Making decisions/plans – we decide how we are going to achieve the objectives i.e. we create a plan
Modelling – as part of the process of creating a plan we will consider different approaches and attempt to assess the consequences of each of these approaches in terms of how much it will cost and how long it will take, and so on.
Implementation – the plan is now carried out
Data collection – we gather information at regular intervals about how the project is progressing. These raw details could be quite numerous and complex on a large project
Data processing – we process the progress data and convert it into ‘information’ which makes it easier for the project managers and others to understand the overall condition of the project
Making decisions/plans – in the light of the comparison of actual project progress with that planned, the plans are modified. This may require the modelling of the outcomes of different possible courses of action
…and so the cycle goes on.

## Slide 5: Responsibilities
Notes: The concept of a reporting hierarchy was introduced in Chapter 1.
The main lesson here is that the details relating to project progress have to originate with the people actually doing the work and have then to be fed up through the management structure. At each management level there is going to be some summarising and commentary before information is passed up to the next level. This means that there is always a danger of ‘information overload’ as information passes from the many to the few.
Site A Floor 1 Floor 2
Site B Floor 1 is 20% complete

## Slide 6: Assessing progress
Checkpoints – predetermined times when progress is checked
  Event driven: check takes place when a particular event has been achieved
  Time driven: date of the check is pre-determined
Frequency of reporting
  The higher the management level then generally the longer the gaps between checkpoints

## Slide 7: Collecting progress details
Need to collect data about:
Achievements / Schedule
Costs
A big problem: how to deal with partial completions
99% completion syndrome
Possible solutions:
Control of products, not activities
Subdivide into lots of sub-activities
Notes: Projects have to be delivered on time and within budget, hence the concern with monitoring achievements and costs.
Partial completion is where, for example, data is being collected at the end of Week 2 of an activity that should take four weeks. We want to know if it is about 50% completed.
An example of the ’99% completion syndrome’ would be in the above case if the developer reported at the end of weeks 1,2 and 3 that the task was respectively 25%, 50% and 75% complete. However at the end of week 4 it is reported that the task is 99% complete. The same thing is reported at the end of week 5 and so on until the task is actually completed.
Control on products implies that actual examination of intermediate allows us to verify independently and objectively that sub-tasks have been completed.

## Slide 8: Red/Amber/Green reporting
Identify key tasks
Break down into sub-tasks
Assess subtasks as:
  Green – ‘on target’
  Amber – ‘not on target but recoverable’
  Red – ‘not on target and recoverable only with difficulty’
Status of ‘critical’ tasks is particularly important
Notes: RAG reporting highlights those activities which need particular attention. The status of a troubled activity might typically move from green to amber; if corrective action is possible it might go back to green, otherwise it could switch to red. If there are lots of instances where activities switch directly from green to red, this could indicate more management control.
‘Critical tasks’ would be those on the critical path and/or reliant on critical resources.

## Slide 9: Gantt charts

## Slide 10: Slip charts
Notes: A slip chart is a version of the Gantt chart where a line is drawn from top to bottom. To the left of the line are all the completed activities and to the right those activities ( or parts of activities) that have not been completed.
The more jagged the line, the more it means that that there are some activities that are lagging to various degrees and some that are ahead of themselves. A very jagged line means that there is scope for re-planning to move resources from those activities that are ahead to those that are behind.

## Slide 11: Cost monitoring
A project could be late because the staff originally committed, have not been deployed
In this case the project will be behind time but under budget
A project could be on time but only because additional resources have been added and so by over budget
Need to monitor both achievements and costs

## Slide 12: Earned value – an example
Tasks
  Specify module 5 days
  Code module 8 days
  Test module 6 days
At the beginning of day 20, PV = 19 days
If everything but testing completed EV = 13 days
Schedule variance = EV-PV i.e. 13-19 = -6
Schedule performance indicator (SPI) = 13/19 = 0.68
Notes: Earned Value Management
PV
Earned Value
A negative schedule variance (SV) means that the project is behind schedule as does a SPI that is less than 1.0.

## Slide 13: Earned value analysis – actual cost
Actual cost (AC) is also known as Actual cost of work performed (ACWP)
In previous example, if
  ‘Specify module’ actually took 3 days
  ‘Code module’ actually took 4 days
Actual cost = 7 days
Cost variance (CV) = EV-AC i.e. 13-7 = 6 days
Cost performance indicator = 13/7 = 1.86
Positive CV or CPI > 1.00 means project under budget

## Slide 14: Project / Program Review
The specific time to review progress is a matter of preference. Different objectives or projects may be reviewed at different time intervals depending on complexity, time span of work, competency level of performer, criticality of work outcomes, disruptions in due dates, resource shortages, and so on. As a rule of thumb, work reviews should be scheduled at least once a month for objectives spanning more than a three-month period. It is never appropriate to wait until just before the planned achievement date to review progress on work objectives.

## Slide 15: Review Process
Quality Assurance (QA) establishes a process by which projects are evaluated to determine whether they are compliant or “at risk.” The QA process uses an approved and published Project Methodology as a baseline for this evaluation. In addition, QA recommends specific action steps for projects at risk of non-compliance.
This review process occurs within different time frames based on project criticality and complexity. Specific procedures must be followed to ensure timely and effective review of deliverables.
Notes: The review is a layered approach, which allows the Review Team to provide advice and counsel to project teams after citing findings during face-to-face-interviews.

## Slide 16: Types of Reviews in Software Testing
Software Peer Review
  Code review
  Pair Programming
  Inspection
  Walkthrough
Software Management review
Software Audit Review

## Slide 17: Software Reviews

## Slide 21: Review Cycle