## Slide 1: TM Tools - S Curve

## Slide 2: Definition
a display of cumulative costs, labour hours or other quantities plotted against time. The name derives from the S-like shape of the curve, flatter at the beginning and end and steeper in the middle, which is typical of most projects.
The beginning represents a slow, deliberate but accelerating start, while the end represents a deceleration as the work runs out

## Slide 3: Types of S Curves
The Baseline S Curve. This S Curve is generated from the Baseline Schedule and / or baseline fields in the Production Schedule.
The Target S Curve. This S Curve is generated from the Production Schedule, assuming all tasks are completed as scheduled.
The Actual S Curve. This S curve is also generated from the Production Schedule, using task percentage complete values to date. The Actual S Curve may also be referred to as the Progress or Progress To Date S Curve.
Notes: http://www.maxwideman.com/guests/s-curve/using.htm

## Slide 4: S-Curve Quantities
Man Hours
Costs
S Curve Quantity Units
  Absolute Values for man hours and / or costs
  Percentage Values for man hours and / or costs

## Slide 5: The Baseline S Curve Prior to project commencement, a schedule is prepared outlining the proposed allocation of resources and the timing of tasks necessary to complete the project within a set time frame and budget. This schedule is referred to as the Baseline Schedule.
Notes: The Baseline Schedule may be used to generate Baseline S‑curves. These S‑curves reflects the planned progress of the Project. If the Project requirements change prior to commencement (e.g. change of scope, delayed start, etc.), the Baseline Schedule may require revision and re-base lining to reflect the changed requirements.

## Slide 6: The Target S Curve
The Target S Curve reflects the progress of the project if all tasks are completed as scheduled. In an ideal world, the Target S Curve will meet the Baseline S Curve at the end of the project (On Time, On Budget) or finish below and to the left of the Baseline S Curve (Finished Early, Under Budget).
In reality, it is not uncommon for the Target S‑curves to finish above and to the right of the Baseline S‑curves (Finished Late, Over Budget). The Target S‑curves will usually change over the duration of the Project due to changes to Task Start Dates and Finish Dates, Man Hours, and/or Cost.

## Slide 7: The Target S Curve

## Slide 8: What Is The Cut Off Date?
The Cut Off Date is the date on which the tasks were physically inspected to determine their percentage complete values.

## Slide 9: Example of Actual S Curves Using Different Cut Off Dates
Notes: At the completion of the Project, with all Tasks 100% complete, the Actual S‑curves will terminate at the Project Completion Date, and be identical to the Target S‑curves. The Actual S‑curves will usually change shape over the duration of the Project due to changes to Task Start Dates and Finish Dates, Man Hours and/or Cost, and Task % Complete to date.
Changing the Cut Off Date after the Producti

## Slide 10: The Man Hours versus Time S Curve
The Costs versus Time S Curve
The Costs versus Time S Curve is shows cumulative costs expended over time for the duration of the project, and may be used to assist in the calculation of the project's cash flow, and cost to complete.
Value and Percentage S Curves
S Curves may be graphed as absolute values (i.e. Man Hours or Costs) versus Time, or as percentage values versus Time.
Value S Curves
Value S Curves are useful for determining the project’s man hours or costs expended to date, and man hours or costs to complete.

## Slide 11: Man Hours versus Time S‑curves
Analysis of the above S-curves reveals the Project as of the 4th of February 2016:
Is 10.5 Man Hours behind schedule (48.5 – 38.0)
Has grown in scope by 5.0 Man Hours (95.0 – 90.0)
Has increased in Duration by 1 Day
Started 1 Day late
Will finish 2 Days late
Will require 57.0 Man Hours to complete (95.0 – 38.0)

## Slide 12: Percentage Man Hours versus Time (Baseline = 100%) S Curves
By setting the Baseline S-curve to finish at 100%, the Project's percentage growth (or contraction) may be compared to the Baseline Schedule, and the Baseline % Complete as of the Cut Off Date may be determined.
Analysis of the given S‑curves reveals the Project as of the 3rd of May 2012:
Has grown in scope by 5.56% (105.56 – 100.00)
Was planned to be 86.67% complete

## Slide 13: Percentage Man Hours versus Time (Target = 100%) S Curves

## Slide 14: Why Use an S Curve?
S Curves allows project managers to quickly identify:
Project Progress
Project Growth or Contraction (Man Hours and / or Costs, Duration)
Project Start and / or Finish Slippage

## Slide 15: Calculating Project Growth using S-curves
Comparison of the Baseline and Target S-curves quickly reveals if the project has grown (Target S-curve finishes above Baseline S-curve) or contracted (Target S-curve finishes below Baseline S-curve) in scope. A change in the project's scopes implies a re-allocation of resources (increase or decrease), and the very possible requirement to raise contract variations. If the resources are fixed, then the duration of the project will increase (finish later) or decrease (finish earlier), possibly leading to the need to submit an extension of time claim.

## Slide 16: Slippage
Slippage is defined as "the amount of time a task has been delayed from its original baseline schedule. The slippage is the difference between the scheduled start or finish date for a task and the baseline start or finish date. Slippage can occur when a baseline plan is set and the actual dates subsequently entered for tasks are later than the baseline dates or the actual durations are longer than the baseline schedule durations".

## Slide 17: Calculating Project Start / Finish Slippage

## Slide 18: S Curve Analysis
The progress of the project is behind target . The Actual S Curve sits below the Target S Curve at the Cut Off Date.
The project has grown in man hours. The Target S Curve finishes above the Baseline S Curve.
The project has grown in duration. The Target S Curve duration is longer than the Baseline S Curve duration.
The project has experienced start slippage, and thus started later than planned . The Target S Curve starts to the right of the Baseline S Curve.
The project has experienced finish slippage, and thus will finish later than planned. The Target S Curve finishes to the right of the Baseline S Curve

## Slide 19: Project Progress
Actual % Complete =
Actual YTD Man Hours @ Cut Off Date / Target Man Hours x 100%
= 38.0 / 95.0 x 100%
= 40.00%
Target % Complete =
Target YTD Man Hours @ Cut Off Date / Target Man Hours x 100%
= 48.5 / 95.0 x 100%
= 51.05%

## Slide 20: Project Growth (Man Hours)
Analysis of the Baseline and Target S Curve data at project completion reveals the project has grown in scope by 5.0 man hours, or 5.56% as compared to the Baseline Schedule.
Project Growth (Man Hours) = Total Target Man Hours – Total Baseline Man Hours
= 95.0 – 90.0
= 5.0
Project % Growth (Man Hours) = ((Target Man Hours / Baseline Man Hours) - 1) x 100%
= ((95.0 / 90.0) - 1) x 100%
= 5.56%

## Slide 21: Project Growth (Duration)
Analysis of the Baseline and Target S Curve data reveals the project has experience a growth in duration of 1 day, or 20.00% as compared to the Baseline Schedule.
Project Growth (Duration) = Target Duration - Baseline Duration
= 6 days – 5 days
= 1 day
Project % Growth (Duration) = ((Target Duration / Baseline Duration) - 1) x 100%
= ((6 days / 5 days) - 1) x 100%
= 20.00%

## Slide 22: Project Start Slippage
Analysis of the Baseline and Target S Curve data reveals the project has a start slippage of 1 day, or 20.00% as compared to the Baseline Schedule.
Start Slippage = Target Start Date – Baseline
=Start Date1st May 2012 – 30th April 2012
=1 day
Start Slippage %
= Start Slippage / Baseline Duration x 100%
=1 day / 5 days x 100%
=20.00%

## Slide 23: Project Finish Slippage
Analysis of the Baseline and Target S Curve data reveals the project has a finish slippage of 2 days, or 40.00% as compared to the Baseline Schedule.
Finish Slippage = Target Finish Date - Baseline Finish Date
= 6th May 2012 – 4th May 2012
= 2 days
Finish Slippage % = Finish Slippage / Baseline Duration x 100%
= 2 days / 5 days x 100%
= 40.00%